## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | MADHURBHASA PIPED WATER SUPPLY SCHEME | SM/13765 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 211/CD | 27/04/2023 | 27/04/2023 | Resource Division | 3.55 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | MADHURBHASA PIPED WATER SUPPLY SCHEME | SM/13765 | New | Charges for new service connection at Madhurbhasa PWSS, P/H-I in the dist of Coochbehar. |  |  | BILL/02016/2024-2025 | BP-440/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 7.68 | 0 | 0 | 0
3 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | MADHURBHASA PIPED WATER SUPPLY SCHEME | SM/13765 | New | Charges for new service connection at Madhurbhasa PWSS, P/H-II |  |  | BILL/01653/2024-2025 | BP-411/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 8.2 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | MADHURBHASA PIPED WATER SUPPLY SCHEME | SM/13765 | New | Execution of different works related to MADHURBHASA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1135/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000616/2022-2023 | 1874/CD | 14/03/2023 | 02/04/2025 | ORIENTAL CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 105.88 | 64.57 | 60.99 | 50
5 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | MADHURBHASA PIPED WATER SUPPLY SCHEME | SM/13765 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000028/2025-2026 | 716/CD | 17/05/2025 | 15/08/2025 | TMC- HI- TECH | 23.44 | 0 | 0 | 0
Total | [13 empty] | 148.75 | 64.57 | 43.41