## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 140/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.77 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Northern Mechanical Division II | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | QUOTATION FOR NSC AT PUTIMARI BAKSHIBASH TW NO I |  |  | BILL/01733/2023-2024 | BP-2023-24-328 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.47 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Execution of different works related to PUTIMARI BAKSIBAS PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 978/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000458/2022-2023 | 1509/CD | 19/01/2023 | 07/07/2025 | NABIN DEBNATH | 396.56 | 270.26 | 68.15 | 75
4 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Northern Mechanical Division II | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Puttimari Baksibas water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001085/2023-2024 | 2781/NMD-II | 05/10/2023 | 04/11/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.49 | 7.35 | 39.77 | 30
5 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | FHTC AT GORBHANGA PWSS |  |  | BILL/01215/2023-2024 | BP-732-P2 | 08/11/2023 | 08/11/2023 | SUPER TECH ENGINEERS CO- OPERATIVE SPOCY.LTD | 30.09 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | HIRING VEHICLE FOR AE/HQ |  |  | BILL/00543/2024-2025 | BP-211 | 31/07/2024 | 31/07/2024 | BHAGWATI BHUJEL | 0.35 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Execution of different works related to PUTIMARI BAKSHIBAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000339/2023-2024 | 1323/CD | 24/11/2023 | 18/03/2025 | NABIN DEBNATH | 31.07 | 0 | 0 | 40
9 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000031/2025-2026 | 597/CD | 28/04/2025 | 23/01/2026 | SHRI ANNAPURNA DISTRIBUTORS | 67.29 | 0 | 0 | 30
11 | COOCHBEHAR | Cooch Behar-II,Mathabhanga-II | Coochbehar Division | PUTIMARI BAKSIBAS PIPED WATER SUPPLY SCHEME. | SM/13816 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000097/2025-2026 | 699/CD | 17/05/2025 | 13/11/2025 | SANKAR BANIK | 25.58 | 0 | 0 | 30
Total | [13 empty] | 20428.5 | 277.62 | 1.36