## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 1351/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bhurkush Water Supply Scheme TW No.- I & II under NMD-II,PHE.Dte,Apd |  |  | ORD/000903/2023-2024 | 2489/NMD-II | 14/08/2023 | 13/09/2023 | ANUP BASU | 21.02 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | laying of DI pipe line along with construction of RCC pillar and sluice valve chamber at BHURKUSH PWSS under Tufanganj Sub-Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000576/2021-2022 | 203/TFG | 07/10/2021 | 06/11/2021 | GOUTAM KUMAR DAS | 2.55 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 151/CD | 27/04/2023 | 27/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | Execution of different works related to BHURKUSH PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1295/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000608/2022-2023 | 1899/CD | 17/03/2023 | 14/08/2023 | AASHIRBAD ENTERPRISE | 106.91 | 104.49 | 97.74 | 90
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000023/2025-2026 | 711/CD | 17/05/2025 | 13/11/2025 | UTTAM SAHA | 21.57 | 0 | 0 | 75
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13859 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000095/2025-2026 | 736/CD | 17/05/2025 | 13/11/2025 | AASHIRBAD ENTERPRISE | 42.14 | 0 | 0 | 85
Total | [13 empty] | 324.68 | 104.49 | 32.18