## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 248/CD | 27/04/2023 | 27/04/2023 | Resource Division | 14.11 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Charges for new service connection at Chhit baralaukuthi PWSS, P/H-I in the dist of Coochbehar. |  |  | BILL/02020/2024-2025 | BP-439/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 7.37 | 0 | 0 | 0
3 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Charges for new service connection at Chhit baralaukuthi PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/02014/2024-2025 | BP-438/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 5.3 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Execution of different works related to CHIT BARA LAUKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000307/2023-2024 | 1281/CD | 10/11/2023 | 02/07/2025 | TMC- HI- TECH | 221.13 | 0 | 0 | 80
5 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Execution of different works related to CHHIT BARA LAUKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000597/2023-2024 | 640/CD | 11/03/2024 | 01/11/2025 | TMC- HI- TECH | 32.91 | 0 | 0 | 70
6 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Chhit Bara Laukuthi Water Supply Scheme TW No.- I under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001151/2024-2025 | 753/NMD-II | 20/02/2025 | 30/06/2025 | GEETA CONSTRUCTION | 10.61 | 0 | 0 | 100
7 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000028/2025-2026 | 716/CD | 17/05/2025 | 15/08/2025 | TMC- HI- TECH | 23.44 | 0 | 0 | 0
8 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
Total | [13 empty] | 382.39 | 0 | 0