## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 248/CD | 27/04/2023 |  | Resource Division | 14.11 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Execution of different works related to CHIT BARA LAUKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000307/2023-2024 | 1281/CD | 10/11/2023 | 08/04/2024 | TMC- HI- TECH | 221.13 | 58.91 | 26.64 | 80
3 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | CHHIT BARA LAUKUTHI PWSS | SM/13865 | New | Execution of different works related to CHHIT BARO LAUKUTHI PWSS under JAL JEEVAN MISSION |  |  | ORD/000597/2023-2024 | 640/CD | 11/03/2024 | 10/05/2024 | TMC- HI- TECH | 32.91 | 0 | 0 | 0
Total | [13 empty] | 268.15 | 58.91 | 21.97