## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR KHATALBARI | SM/13877 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sajerpar Kathalbari water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/000830/2023-2024 | 2411/NMD-II | 10/08/2023 | 09/09/2023 | S.D CONCERN WORKSHOP | 18.54 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 143/CD | 27/04/2023 | 27/04/2023 | Resource Division | 10.69 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | exc. of difft. works at takagach pwss |  |  | BILL/00788/2023-2024 | BP-345 | 20/07/2023 | 20/07/2023 | KARTICK CH SEAL | 2.08 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | EXC. OF DIFFERENT WORKS AT BHANGAMORE PWSS |  |  | BILL/00634/2023-2024 | BP-316-P2 | 17/07/2023 | 17/07/2023 | NABIN DEBNATH | 7.58 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Execution of different works related to SAJHERPAR KHATALBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000588/2022-2023 | 1676/CD | 13/02/2023 | 13/07/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO | 361.38 | 196.05 | 54.25 | 65
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Name of Work: Execution of different works related to SHAJERPAR KATHALBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000275/2023-2024 | 1042/CD | 22/09/2023 | 21/11/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO | 27.93 | 0 | 0 | 45
7 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | FABRICATION AND INSTALLATION OF LAND POSSESSION SB AT EVERY LANDS OF DIFFERENT (CHAUDANGA) PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-D) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000508/2024-2025 | 1793/CD | 30/09/2024 | 10/10/2024 | MAKHMALI ACTIVITY CLUSTER | 30.35 | 0 | 0 | 90
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | EXECUTION OF DIFFERENT WORKS RELATED TO SAJHERPAR KHATALBARI CHAKCHAKA ZONE II MARANADIRKUTHI & GOPALPUR PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000533/2024-2025 | 2217/CD | 23/12/2024 | 20/08/2025 | MATARA CONSTRUCTION CO. | 80.28 | 0 | 0 | 80
10 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000270/2025-2026 | 744/CD | 17/05/2025 | 15/08/2025 | MS BIDYUT SARKAR | 34.33 | 0 | 0 | 0
11 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | SAJHERPAR KHATALBARI | SM/13877 | New | NEW SERVICE CONNECTION CHARGES AT SAJHERPAR KATHALBARI PH-II |  |  | BILL/03153/2023-2024 | BP-474/24-25 | 17/03/2025 | 17/03/2025 | WBSEDCL | 15.28 | 0 | 0 | 0
Total | [13 empty] | 20377.74 | 196.05 | 0.96