## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 143/CD | 27/04/2023 |  | Resource Division | 10.69 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | SAJHERPAR KHATALBARI | SM/13877 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sajerpar Kathalbari water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/000830/2023-2024 | 2411/NMD-II | 10/08/2023 | 09/09/2023 | S.D CONCERN WORKSHOP | 18.54 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Name of Work: Execution of different works related to SHAJERPAR KATHALBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000275/2023-2024 | 1042/CD | 22/09/2023 | 21/11/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO | 27.93 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | EXC. OF DIFFERENT WORKS AT BHANGAMORE PWSS |  |  | BILL/00634/2023-2024 | BP-316-P2 | 17/07/2023 |  | NABIN DEBNATH | 7.58 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | exc. of difft. works at takagach pwss |  |  | BILL/00788/2023-2024 | BP-345 | 20/07/2023 |  | KARTICK CH SEAL | 2.08 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Execution of different works related to SAJHERPAR KHATALBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000588/2022-2023 | 1676/CD | 13/02/2023 | 13/07/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO | 361.38 | 170.09 | 47.07 | 45
7 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | NEW SERVICE CONNECTION CHARGES AT SAJHERPAR KATHALBARI PH-II |  |  | BILL/02090/2023-2024 | null | 19/02/2024 |  | WBSEDCL | 15.28 | 0 | 0 | null
8 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | NEW SERVICE CONNECTION CHARGES AT SAJHERPAR KATHALBARI PH-I |  |  | BILL/02091/2023-2024 | null | 19/02/2024 |  | WBSEDCL | 18.84 | 0 | 0 | null
9 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | SAJHERPAR KHATALBARI | SM/13877 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20251.62 | 170.09 | 0.84