## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | QUOTATION FOR NSC AT DEBOGRAM PH NO I |  |  | BILL/01045/2023-2024 | BP-2023-24-244 | 27/07/2023 |  | WBSEDCL | 5.05 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | QUOTATION FOR NSC AT DEBGRAM PH NO II |  |  | BILL/01046/2023-2024 | BP-2023-24-245 | 27/07/2023 |  | WBSEDCL | 1.7 | 0 | 0 | 0
3 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-D) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000401/2023-2024 | 1418/CD | 08/12/2023 | 22/01/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
4 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-E) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000402/2023-2024 | 1419/CD | 08/12/2023 | 22/01/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
5 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-F) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000403/2023-2024 | 1420/CD | 08/12/2023 | 22/01/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
6 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | EXECUTION OF DIFFERENT WORK AT UTTAR FULKARDABRI PWSS |  |  | BILL/02013/2023-2024 | BP-1390-P2 | 31/03/2024 |  | PARITOSH PANDIT | 0.09 | 0 | 0 | 0
7 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
8 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | Execution of different works related to DEBGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000423/2023-2024 | 1479/CD | 20/12/2023 | 18/02/2024 | GOUTAM KUMAR DAS | 47.59 | 12.91 | 27.12 | 61
9 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Debgram water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000329/2023-2024 | 1607/NMD-II | 17/07/2023 | 16/08/2023 | M.S ENTERPRISE | 21.28 | 20.99 | 98.67 | 100
10 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | Execution of different works related to DEBGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000591/2022-2023 | 1673/CD | 13/02/2023 | 13/07/2023 | GOUTAM KUMAR DAS | 326.41 | 213.38 | 65.37 | 90
11 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | DEBGRAM PIPED WATER SUPPLY SCHEME | SM/13880 | New | Execution of different works related to DEBGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000122/2023-2024 | 641/CD | 12/07/2023 | 10/09/2023 | GOUTAM KUMAR DAS | 98.08 | 43.41 | 44.26 | 90
Total | [13 empty] | 558.82 | 293.6 | 52.54