## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 212/CD | 27/04/2023 | 27/04/2023 | Resource Division | 19.9 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JHINGAPUNNI PWSS TW NO -I |  |  | BILL/01429/2023-2024 | BP-2023-24-281 | 18/08/2023 | 18/08/2023 | WBSEDCL | 5.32 | 0 | 0 | 0
3 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JHINGAPUNNI PWSS TW NO -II |  |  | BILL/01427/2023-2024 | BP-2023-24-275 | 18/08/2023 | 18/08/2023 | WBSEDCL | 6.96 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | Execution of different works related to JHINGAPUNI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1001/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000485/2022-2023 | 1550/CD | 24/01/2023 | 23/06/2023 | MATRI ENTERPRISEES | 266 | 188.79 | 70.97 | 85
5 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | EXECUTION OF DIFFERENT WORKS RELATED TO JHINGAPUNI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000599/2024-2025 | 2300/CD | 23/12/2024 | 21/02/2025 | MATRI ENTERPRISEES | 55.86 | 0 | 0 | 0
6 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
7 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within TATERKUTHI & JHINGAPUNI area) MAHISKUCHI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000594/2024-2025 | 2278/CD | 23/12/2024 | 21/02/2025 | UTPAL CHAKRABORTY | 66.76 | 0 | 0 | 70
8 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within area MANTANI JHINGAPUNI) SHILGHAGRI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000608/2024-2025 | 2309/CD | 23/12/2024 | 21/06/2025 | GOUTAM KUMAR DAS | 52.39 | 0 | 0 | 70
9 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | JHINGAPUNI PIPED WATER SUPPLY SCHEME | SM/13881 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jhingapuni water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000716/2023-2024 | 2100/NMD-II | 26/07/2023 | 01/05/2025 | HARAGOURI ENTERPRISE | 18.49 | 13.17 | 71.2 | 100
Total | [13 empty] | 20280.99 | 201.96 | 1