## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Execution of different works related to KHAGRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000343/2023-2024 | 1327/CD | 24/11/2023 | 23/01/2024 | DAS ENTERPRISE | 15.07 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000358/2023-2024 | 1342/CD | 24/11/2023 | 23/01/2024 | DAS ENTERPRISE | 1.32 | 0 | 0 | 0
3 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | New service connection at Khagribari PWSS, P/H-I |  |  | BILL/00200/2024-2025 | BP-48/24-25 | 29/04/2024 |  | WBSEDCL | 4.85 | 0 | 0 | null
4 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | New service connection at Khagribari PWSS, P/H-I |  |  | BILL/00200/2024-2025 | BP-48/24-25 | 29/04/2024 |  | WBSEDCL | 4.85 | 0 | 0 | null
5 | COOCHBEHAR | Tufanganj - II | Northern Mechanical Division II | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | New service connection at Khagribari PWSS, P/H-II |  |  | BILL/00199/2024-2025 | BP-47/24-25 | 29/04/2024 |  | WBSEDCL | 3.57 | 0 | 0 | null
6 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Execution of different works related to KHAGRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000602/2023-2024 | 646/CD | 11/03/2024 | 10/05/2024 | HIRAK CONSTRUCTION | 52.26 | 0 | 0 | 30
7 | COOCHBEHAR | Tufanganj - II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Execution of different works related to KHAGRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000554/2022-2023 | 1703/CD | 13/02/2023 | 13/07/2023 | HIRAK CONSTRUCTION | 250.06 | 145.3 | 58.1 | 90
Total | [13 empty] | 331.98 | 145.3 | 43.77