## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000358/2023-2024 | 1342/CD | 24/11/2023 | 23/01/2024 | DAS ENTERPRISE | 1.32 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Execution of different works related to KHAGRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000602/2023-2024 | 646/CD | 11/03/2024 | 10/05/2024 | HIRAK CONSTRUCTION | 52.26 | 0 | 0 | 30
3 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | New service connection at Khagribari PWSS, P/H-II |  |  | BILL/00199/2024-2025 | BP-47/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.57 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | New service connection at Khagribari PWSS, P/H-I |  |  | BILL/00200/2024-2025 | BP-48/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 4.85 | 0 | 0 | 0
5 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000092/2025-2026 | z28 | 05/07/2025 | 03/10/2025 | HIRAK CONSTRUCTION | 34.42 | 0 | 0 | 0
6 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Execution of different works related to KHAGRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000554/2022-2023 | 1703/CD | 13/02/2023 | 29/12/2025 | HIRAK CONSTRUCTION | 250.06 | 0 | 0 | 90
7 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TATERKUTHI KHAGRIBARI GORBHANGA & FALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000557/2024-2025 | 2242/CD | 23/12/2024 | 21/02/2025 | HARIDAS GHOSH | 65.94 | 0 | 0 | 60
8 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Hiring of Inspection Vehicle (Diesel) for office of the Assistant Engineer, Coochbehar Mechanical Sub-Division I.C.W. JJM works under NMD-II PHE Dte. |  | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001326/2024-2025 | 399/CMSD | 28/03/2025 | 28/05/2025 | DIPAK SARKAR | 0.77 | 0 | 0 | 0
9 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | KHAGRIBARI PIPED WATER SUPPLY SCHEME | SM/13882 | New | Hiring of Inspection Vehicle (Diesel) for office of the Assistant Engineer, Coochbehar Mechanical Sub-Division I.C.W. JJM works under NMD-II PHE Dte. |  | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001320/2024-2025 | 101/CMSD | 22/01/2025 | 22/03/2025 | DIPAK SARKAR | 0.77 | 0 | 0 | 100
Total | [13 empty] | 413.96 | 0 | 0