## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 113/CD | 26/04/2023 |  | Resource Division | 54.24 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | QUOTATION FOR NSC AT BARARANGRASH TW NO I,Z-I(H/O) SITE |  |  | BILL/01734/2023-2024 | BP-2023-24-317 | 27/09/2023 |  | WBSEDCL | 7.29 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | QUOTATION FOR NSC AT BARARANGRASH TW NO II,Z-II(H/O) SITE |  |  | BILL/01735/2023-2024 | BP-2023-24-316 | 27/09/2023 |  | WBSEDCL | 6.78 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 25/CD | 05/01/2024 |  | Resource Division | 35.4 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bararangrass water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000786/2023-2024 | 2341/NMD-II | 01/08/2023 | 31/08/2023 | AHALYA ENGINEERING WORKS | 45.52 | 18.9 | 41.51 | 40
6 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | New service connection charges for BARARANGARASH , ZONE- II, PH - II , UNDER NMD-II, PHE,DTE. |  |  | BILL/02618/2023-2024 | BP-2023-24-584 | 01/02/2024 |  | WBSEDCL | 12.5 | 0 | 0 | null
7 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGARAS Z II PWSS under JAL JEEVAN MISSION |  |  | ORD/000470/2023-2024 | 272/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 87.57 | 74.83 | 85.45 | 86
8 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGARAS Z I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000491/2023-2024 | 293/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 87.57 | 62.5 | 71.37 | 73
9 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to B.RANGARAS Z1 PWSS under JAL JEEVAN MISSION |  |  | ORD/000541/2023-2024 | 629/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 71.73 | 62.56 | 87.22 | 87
10 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | NEW SERVICE CONNECTION CHARGES AT BARARANG RASH ZONE-I, PH-II |  |  | BILL/03030/2023-2024 | BP-2023-24-684 | 14/03/2024 |  | WBSEDCL | 8.23 | 0 | 0 | null
11 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | NEW SERVICE CONNECTION CHARGES AT BARARANG RASH ZONE-I, PH-II |  |  | BILL/03030/2023-2024 | BP-2023-24-684 | 14/03/2024 |  | WBSEDCL | 8.23 | 0 | 0 | null
12 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to B.RANGARAS Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000578/2023-2024 | 618/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 69.7 | 0 | 0 | 50
13 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to under JAL JEEVAN MISSION as |  |  | ORD/000152/2023-2024 | 1398 | 23/05/2023 | 22/07/2023 | A K SIKDAR | 0.88 | 0 | 0 | 0
14 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGRAS (ZONE-II) PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1237/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000544/2022-2023 | 1784/CD | 02/03/2023 | 30/07/2023 | MS SSB CONSTRUCTION CO | 735.62 | 523.43 | 71.16 | 88
15 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGRAS (ZONE-I) PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1211/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000543/2022-2023 | 1783/CD | 02/03/2023 | 30/07/2023 | MS SSB CONSTRUCTION CO | 667.63 | 396.38 | 59.37 | 66
16 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part I | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000587/2023-2024 | 624/CD | 11/03/2024 | 10/05/2024 | RHYNO INFRASTRUCTURE | 99.34 | 0 | 0 | 100
17 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGRAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000059/2024-2025 | 1298/CD | 11/07/2024 | 09/10/2024 | MS SSB CONSTRUCTION CO | 86.19 | 0 | 0 | 35
Total | [13 empty] | 21873.7 | 1138.59 | 5.21