## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 113/CD | 26/04/2023 | 26/04/2023 | Resource Division | 54.24 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | QUOTATION FOR NSC AT BARARANGRASH TW NO I,Z-I(H/O) SITE |  |  | BILL/01734/2023-2024 | BP-2023-24-317 | 27/09/2023 | 27/09/2023 | WBSEDCL | 7.29 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | QUOTATION FOR NSC AT BARARANGRASH TW NO II,Z-II(H/O) SITE |  |  | BILL/01735/2023-2024 | BP-2023-24-316 | 27/09/2023 | 27/09/2023 | WBSEDCL | 6.78 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGRAS (ZONE-II) PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1237/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000544/2022-2023 | 1784/CD | 02/03/2023 | 30/07/2023 | MS SSB CONSTRUCTION CO | 735.62 | 653.5 | 88.84 | 88
5 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGRAS (ZONE-I) PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1211/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000543/2022-2023 | 1783/CD | 02/03/2023 | 30/07/2023 | MS SSB CONSTRUCTION CO | 667.63 | 616.38 | 92.32 | 66
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to under JAL JEEVAN MISSION as |  |  | ORD/000152/2023-2024 | 1398 | 23/05/2023 | 22/07/2023 | A K SIKDAR | 0.88 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGARAS Z II PWSS under JAL JEEVAN MISSION | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000470/2023-2024 | 272/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 87.57 | 74.83 | 85.45 | 86
8 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGARAS Z I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000491/2023-2024 | 293/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 87.57 | 62.5 | 71.37 | 73
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to B.RANGARAS Z1 PWSS under JAL JEEVAN MISSION | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000541/2023-2024 | 629/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 71.73 | 62.56 | 87.22 | 87
10 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to B.RANGARAS Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000578/2023-2024 | 618/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 69.7 | 67.34 | 96.61 | 50
11 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Execution of different works related to BARARANGRAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000059/2024-2025 | 1298/CD | 11/07/2024 | 09/10/2024 | MS SSB CONSTRUCTION CO | 86.19 | 84.78 | 98.37 | 35
12 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part I | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000587/2023-2024 | 624/CD | 11/03/2024 | 10/05/2024 | RHYNO INFRASTRUCTURE | 99.34 | 48.27 | 48.59 | 100
13 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 25/CD | 05/01/2024 | 05/01/2024 | Resource Division | 35.4 | 0 | 0 | 0
14 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | New service connection charges for BARARANGARASH , ZONE- II, PH - II , UNDER NMD-II, PHE,DTE. |  |  | BILL/02618/2023-2024 | BP-2023-24-584 | 01/02/2024 | 01/02/2024 | WBSEDCL | 12.5 | 0 | 0 | 0
15 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | NEW SERVICE CONNECTION CHARGES AT BARARANG RASH ZONE-I, PH-II |  |  | BILL/03030/2023-2024 | BP-2023-24-684 | 14/03/2024 | 14/03/2024 | WBSEDCL | 8.23 | 0 | 0 | 0
16 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bararangrass water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000786/2023-2024 | 2341/NMD-II | 01/08/2023 | 31/05/2025 | AHALYA ENGINEERING WORKS | 45.52 | 37.8 | 83.03 | 90
17 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
18 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
19 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | Solarization of grid connected pumping installation at Different PWSS at Coochbehar-II Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000136/2025-2026 | 1336/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 21.84 | 0 | 0 | 0
20 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000329/2025-2026 | 704/CD | 17/05/2025 | 12/01/2026 | MS SSB CONSTRUCTION CO | 85.29 | 0 | 0 | 100
21 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | BARARANGRAS PIPED WATER SUPPLY SCHEME | SM/14135 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000272/2025-2026 | 1499/CD | 11/08/2025 | 09/11/2025 | AASHIRBAD ENTERPRISE | 24.05 | 0 | 0 | 60
Total | [13 empty] | 22484.71 | 1707.95 | 7.6