## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Execution of different works related to KHARI ANALDHONDRA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1231/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000550/2022-2023 | 1786/CD | 02/03/2023 | 03/09/2025 | GHOSH AND SAHA CONSTRUCTION | 649.01 | 570.32 | 87.88 | 85
2 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | KHARI ANALDHONDRA PWSS | SM/14136 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Khari Analdhondra Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001149/2023-2024 | 2901/NMD-II | 19/10/2023 | 18/11/2023 | M/S SAJAHAN CHOWDHURY | 21.45 | 14.77 | 68.88 | 100
3 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Execution of different works related to KHARI ANALDHANDRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000348/2023-2024 | 1332/CD | 24/11/2023 | 23/01/2024 | GHOSH AND SAHA CONSTRUCTION | 5.29 | 4.57 | 86.36 | 30
4 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 102/CD | 26/04/2023 | 26/04/2023 | Resource Division | 15.65 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | KHARI ANALDHONDRA PWSS | SM/14136 | New | QUOTATION FOR NSC AT KHARIJA ANALDHONDRA TW NO-II |  |  | BILL/01797/2023-2024 | BP-2023-24-311 | 27/09/2023 | 27/09/2023 | WBSEDCL | 16.49 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | KHARI ANALDHONDRA PWSS | SM/14136 | New | QUOTATION FOR NSC AT KHARIJA ANALDHONDRA TW NO-I |  |  | BILL/01799/2023-2024 | BP-2023-24-310 | 27/09/2023 | 27/09/2023 | WBSEDCL | 7.97 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Execution of different works related to KHARI ANALDHONDRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000471/2023-2024 | 273/CD | 09/02/2024 | 03/02/2025 | GHOSH AND SAHA CONSTRUCTION | 94.82 | 84.78 | 89.41 | 35
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part E | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000582/2023-2024 | 599/CD | 11/03/2024 | 09/06/2024 | LIMRA SOCIAL WELFARE SOCIETY | 25.98 | 25.91 | 99.74 | 100
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 66/CD | 11/01/2024 | 11/01/2024 | Resource Division | 17.2 | 0 | 0 | 0
11 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | KHARI ANALDHONDRA PWSS | SM/14136 | New | PAYMENT OF 06 NOS LABORATORY UNDER COB DIVISION, PHED |  |  | BILL/01085/2024-2025 | BP-221 | 01/08/2024 | 01/08/2024 | GREEN ECONOMY INISTIVES PVT LTD | 0.07 | 0 | 0 | 0
Total | [13 empty] | 20643.23 | 700.35 | 3.39