## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | QUOTATION FOR NEW SERVICE CONNECTION AT UNISHBISHA TW NO -II |  |  | BILL/00090/2023-2024 | BP-2023-24-83 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | QUOTATION FOR NEW SERVICE CONNECTION AT UNISHBISHA TW NO -I |  |  | BILL/00089/2023-2024 | BP-2023-24-76 | 15/05/2023 | 15/05/2023 | WBSEDCL | 0.93 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part I | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000587/2023-2024 | 624/CD | 11/03/2024 | 10/05/2024 | RHYNO INFRASTRUCTURE | 99.34 | 29.1 | 29.29 | 100
4 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 15/CD | 05/01/2024 | 05/01/2024 | Resource Division | 20.71 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | FUEL BILL |  |  | BILL/00588/2024-2025 | BP-222 | 01/08/2024 | 01/08/2024 | SUCHITRO FUEL STATION | 0.6 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Execution of different works related to UNISH BASA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1235/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000551/2022-2023 | 1787/CD | 02/03/2023 | 25/08/2025 | M/S KAMAK ENGINEERS AND CO | 645.73 | 541.47 | 83.85 | 40
7 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for UNISH BASA (Mathabhanga-II Block) water supply scheme, TW no I, II and III under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000707/2023-2024 | 2225/NMD-II | 28/07/2023 | 31/08/2025 | SARKAR ELECTRIC | 32 | 26.58 | 83.07 | 60
8 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Execution of different works related to UNISH BASA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000494/2023-2024 | 296/CD | 09/02/2024 | 03/02/2025 | UNIVERSAL CONSTRUCTION | 78.77 | 13.52 | 17.17 | 30
9 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 286.45 | 1.45 | 20
10 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | EXECUTION OF DIFFERENT WORKS (within ANGARKATA PARADUBI & DUAI SUAI area) RELATED TO UNISHBASHA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000681/2024-2025 | 87/CD | 17/01/2025 | 18/03/2025 | M/S KAMAK ENGINEERS AND CO | 89.87 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASUNDAR and others) under JJM in the BLOCK: Mathabhanga-II, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000168/2025-2026 | 1387/NMD-II | 26/06/2025 | 26/07/2025 | A.K SIKDAR | 18.14 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme UNISH BASA (BLOCK-Mathabhanga-II) | SM/14137 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000266/2025-2026 | 768/CD | 17/05/2025 | 15/08/2025 | MANABENDRA DE | 28.01 | 0 | 0 | 0
Total | [13 empty] | 21292.5 | 897.12 | 4.21