## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ANGRAKATA PARADUBI TW NO -II |  |  | BILL/00091/2023-2024 | BP-2023-24-84 | 15/05/2023 |  | WBSEDCL | 0.93 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ANGRAKATA PARADUBI TW NO -I |  |  | BILL/00092/2023-2024 | BP-2023-24-85 | 15/05/2023 |  | WBSEDCL | 0.93 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Angrakata Paradubi Water Supply Scheme TW No.- I ,II,III and IV under NMD-II,PHE.Dte,APD. |  |  | ORD/001247/2023-2024 | 2974/NMD-II | 22/11/2023 | 22/12/2023 | P K ENGINEERING | 42.68 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 16/CD | 05/01/2024 |  | Resource Division | 25.77 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | Execution of different works related to ANGARKATA PARADUBI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1236/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000601/2022-2023 | 1790/CD | 02/03/2023 | 30/07/2023 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 820.23 | 459.61 | 56.03 | 55
6 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | Execution of different works related to A. PARADUBI PWSS under JAL JEEVAN MISSION B |  |  | ORD/000588/2023-2024 | 625/CD | 11/03/2024 | 10/05/2024 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 95.9 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | Execution of different works related to A. PARADUBI PWSS under JAL JEEVAN MISSION |  |  | ORD/000568/2023-2024 | 610/CD | 11/03/2024 | 10/05/2024 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 96.86 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | Execution of different works related to MUKUL DANGA PWSS under JAL JEEVAN MISSION |  |  | ORD/000076/2024-2025 | 1186/CD | 18/06/2024 | 16/09/2024 | SHREE RANI SATI ENTERPRISE | 76.56 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANGARKATA PARADUBI | SM/14138 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20949.14 | 459.61 | 2.19