## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 181/CD | 27/04/2023 | 27/04/2023 | Resource Division | 57.7 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for JORPATKI water supply scheme, TW no I, II, III and IV under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000880/2023-2024 | 2454/NMD-II | 11/08/2023 | 10/09/2023 | M/S P.P ELECTRICALS | 42.38 | 0 | 0 | 50
3 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within JORPATKI area) CHUNGERKHATA KHAGRIBARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000596/2024-2025 | 2297/CD | 23/12/2024 | 21/02/2025 | JAINCO TRADERS | 81.98 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Providing FHTC, Repairing of OHR and laying new Pipe line and other allied works in-connection with augmentation of BARA KAIMARI PWSS under Cooch Behar Division, PHED.(Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000032/2022-2023 | 90/CD | 18/04/2022 | 17/07/2022 | M/S. NITYAGOPAL BANIK | 127.85 | 0 | 0 | 1
5 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Providing FHTC, Construction of pump house, Boundary wall at 3rd T/W site and laying of Pipe line and other allied works in-connection with augmentation of BARA KAIMARI PWSS under Cooch Behar Division, PHED. (Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000034/2022-2023 | 93/CD | 18/04/2022 | 16/08/2022 | NABIN DEBNATH | 126.1 | 0 | 0 | 1
6 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Execution of different works related to JORPATKI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000049/2023-2024 | 488/CD | 05/06/2023 | 02/11/2023 | SANJAY MANDAL | 2.27 | 0 | 0 | 100
7 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 14/CD | 05/01/2024 | 05/01/2024 | Resource Division | 24.45 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT JOREPATKI TW I |  |  | BILL/00340/2024-2025 | BP-112/24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | EXECUTION OF DIFFERENT WORK AT BOKNABANDHA PWSS |  |  | BILL/01970/2023-2024 | BP-1058-P3 | 13/02/2024 | 13/02/2024 | MS BIDYUT SARKAR | 0.2 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | SUPPLY OF CI SPECIALS AT JAMALDAHAT PWSS |  |  | BILL/02060/2023-2024 | BP-1394 | 31/03/2024 | 31/03/2024 | SSPR VALVE MANUFACTURING PVT. LTD. | 9.66 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | supply of fuel under coochbehar division phed |  |  | BILL/01849/2023-2024 |  | 25/03/2024 | 25/03/2024 | R.C.BANIK & SONS | 7.03 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION CHARGES AT JOREPATKI TW II |  |  | BILL/00339/2024-2025 | BP-111/24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
14 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Execution of different works related to JORPATKI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1233/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000596/2022-2023 | 1788/CD | 02/03/2023 | 18/08/2025 | M/S KAMAK ENGINEERS AND CO | 900.09 | 0 | 0 | 80
15 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Execution of different works related to AUG. of BARO SOULMARI SINGIJANI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000409/2023-2024 | 1376/CD | 05/12/2023 | 03/02/2024 | GOUTAM KUMAR DAS | 9.91 | 0 | 0 | 0
16 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Execution of different works related to AUG. of BARO SOULMARI SINGIJANI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000408/2023-2024 | 1375/CD | 05/12/2023 | 03/02/2024 | GOUTAM KUMAR DAS | 9.91 | 0 | 0 | 0
17 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
18 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | EXECUTION OF DIFFERENT WORKS (within BALASUNDAR and JORPATKI area) RELATED TO SHIKARPUR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000678/2024-2025 | 83/CD | 17/01/2025 | 18/03/2025 | BIJOY ROY | 59.97 | 0 | 0 | 0
19 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Wall Painting, Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part C | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000508/2023-2024 | 305/CD | 09/02/2024 | 31/01/2025 | LIMRA SOCIAL WELFARE SOCIETY | 52.96 | 0 | 0 | 82
20 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Execution of different works related to JORPATKI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000600/2023-2024 | 645/CD | 11/03/2024 | 06/03/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 96.98 | 0 | 0 | 70
21 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Execution of different works (within JORPATKI area) related to Aug. of BSOLMARI-SINGIJANI PWSS under JAL JEEVAN MISSION |  |  | ORD/000048/2024-2025 | 1156/CD | 14/06/2024 | 13/08/2024 | GOUTAM KUMAR DAS | 97 | 0 | 0 | 0
22 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
23 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Execution of different works (within JORPATKI area) related to CHAKIARCHHARA RUNIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000665/2024-2025 | 93/CD | 17/01/2025 | 13/07/2025 | KAJAL KUMAR DE | 69.32 | 0 | 0 | 55
24 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000059/2025-2026 | 695/CD | 16/05/2025 | 12/11/2025 | M/S JAYA SARKAR | 12.09 | 0 | 0 | 65
25 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASI and others) under JJM in the BLOCK: Mathabhanga-I, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000139/2025-2026 | 1348/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 34.38 | 0 | 0 | 0
26 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | Solarization of grid connected pumping installation at Different PWSS at Mathabhanga-I Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000167/2025-2026 | 1388/NMD-II | 26/06/2025 | 24/09/2025 | E AND C ENGINEERING & CONSULTANCY SERVICES PRIVATE LIMITED | 47.89 | 0 | 0 | 0
27 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000077/2025-2026 | 650/CD | 05/05/2025 | 30/01/2026 | SUPER -TECH ENGINEERS'CO-OPERATIVE SOCIETY LIMITED | 69.03 | 0 | 0 | 60
28 | COOCHBEHAR | Mathabhanga-I,Mathabhanga-II | Coochbehar Division | GROUND WATER BASED JORPATKI PIPED WATER SUPPLY SCHEME. | SM/14139 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000076/2025-2026 | 649/CD | 05/05/2025 | 03/08/2025 | GOUTAM KUMAR DAS | 67.3 | 0 | 0 | 0
Total | [13 empty] | 22339.08 | 0 | 0