## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Providing 140 Nos. F.H.T.C. Connection in the commend area at Kalarayerkuthi W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000473/2021-2022 | 717/SD | 18/03/2022 | 02/04/2022 | SANKAR BANIK | 4.91 | 4.91 | 99.92 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | LAYING OF DI PIPE LINE (Pundibari to Baneswar) AT KALARAYER KUTHE (ZONE-I) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000478/2022-2023 | 1533/CD | 20/01/2023 | 20/04/2023 | SANKAR BANIK | 15.77 | 15.76 | 99.97 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHTC LAYING OF PIPE LINE AT KALARAYER KUTHE (ZONE-III) PWSS under JAL JEEVAN MISSION (PART ¿A2) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000481/2022-2023 | 1536/CD | 20/01/2023 | 20/04/2023 | BISWAJIT GUHA | 69.02 | 43.66 | 63.25 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-A) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000760/2022-2023 | 1268/CD. | 01/12/2022 | 08/12/2022 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-B) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000761/2022-2023 | 1403/CD | 23/12/2022 | 30/12/2022 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000762/2022-2023 | 1445/CD | 05/01/2023 | 12/01/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-F) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000765/2022-2023 | 1756/CD | 27/02/2023 | 06/03/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-I) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000768/2022-2023 | 1830/CD | 06/03/2023 | 13/03/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-E) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000764/2022-2023 | 1754/CD | 27/02/2023 | 06/03/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-G) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000766/2022-2023 | 1767/CD | 02/03/2023 | 09/03/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 1
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-H) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000767/2022-2023 | 1794/CD | 03/03/2023 | 10/03/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 1
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Execution of different works related to KALARAYERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000749/2022-2023 | 1809/CD | 03/03/2023 | 02/04/2023 | SANKAR BANIK | 4.89 | 3.45 | 70.68 | 1
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-D) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000763/2022-2023 | 1740/CD | 21/02/2023 | 28/02/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference under Cooch Behar Division, PHED. (Part-L) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000816/2022-2023 | 1946/CD W | 22/03/2023 | 29/03/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 1
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 138/CD | 27/04/2023 |  | Resource Division | 51.53 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | HIRING DISEL VEHICLE OF BOLERO MAXI CAB FOR O/O THE A.Engg./RWS, PHED |  |  | BILL/00640/2022-2023 | BP-782-2022-23 | 14/03/2023 |  | AJAD HOSSAIN | 0.37 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000822/2022-2023 | 2000/CD | 29/03/2023 | 28/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Execution of different works related to KALARAYERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000783/2022-2023 | 1699/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 8.6 | 3.79 | 44.04 | 100
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHTC LAYING OF PIPE LINE AT KALARAYER KUTHE (ZONE-II) PWSS under JAL JEEVAN MISSION (PART ¿C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000480/2022-2023 | 1535/CD | 20/01/2023 | 20/04/2023 | CHAKRABORTY ENTERPRISE. | 99.82 | 79.4 | 79.54 | 80
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | EXC. OF DIFF. WORK AT KALARAYER KUTHI PWSS |  |  | BILL/00544/2023-2024 | null | 06/04/2023 |  | SANKAR BANIK | 3 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Execution of different works related to PART B of KALARAYER KUTHE (ZONE-I) PWSS 3RD Site under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000774/2022-2023 | 1661/CD | 10/02/2023 | 11/04/2023 | NANDA DULAL GHOSH | 61.34 | 35.92 | 58.57 | 61
22 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | QUOTATION FOR NSC AT kalarayerkuthi TW NO-II,z-iii |  |  | BILL/01844/2023-2024 | BP-2023-24-392 | 06/10/2023 |  | WBSEDCL | 9.69 | 0 | 0 | 0
23 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | QUOTATION FOR NSC AT kalarayerkuthi TW NO-III,Z--iii |  |  | BILL/01843/2023-2024 | BP-2023-24-390 | 06/10/2023 |  | WBSEDCL | 6.7 | 0 | 0 | 0
24 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | QUOTATION FOR NSC AT kalarayerkuthi TW NO-I,Z-III |  |  | BILL/01864/2023-2024 | BP-2023-24-389 | 06/10/2023 |  | WBSEDCL | 5.57 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHTC LAYING OF PIPE LINE AT KALARAYER KUTHE (ZONE-III) PWSS under JAL JEEVAN MISSION (PART ¿A3) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000474/2022-2023 | 1529/CD | 20/01/2023 | 20/04/2023 | TAPU BANIK | 64.86 | 12.73 | 19.63 | 73
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Sinking of Big Dia Tubewell at HWSite & 2nd & 3rd Site of KALARAYERKUTHI ZONE ¿ III PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000471/2022-2023 | 1526/CD | 20/01/2023 | 20/04/2023 | TAPAN CHANDA | 35.11 | 0 | 0 | 100
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Providing FHTC Laying Of Pipe Line And Construction Of Boundary Wall And Pump House At 2nd Site At KALARAYER KUTHE (ZONE-III) PWSS under JAL JEEVAN MISSION (Part-B2) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000477/2022-2023 | 1532/CD | 20/01/2023 | 20/04/2023 | MALAY KR.DEB | 88.77 | 58.52 | 65.92 | 70
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHTC LAYING OF PIPE LINE AT KALARAYER KUTHE PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000319/2022-2023 | 928/CD | 26/09/2022 | 26/10/2022 | SANKAR BANIK | 5.23 | 5.18 | 99.1 | 40
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Providing FHTC Laying Of Pipe Line And Construction Of Boundary Wall And Pump House At 2nd Site At KALARAYER KUTHE (ZONE-II) PWSS under JAL JEEVAN MISSION (Part-B1) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000473/2022-2023 | 1528/CD | 20/01/2023 | 29/06/2023 | HIRAK CONSTRUCTION | 94.67 | 6.59 | 6.97 | 60
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part A | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000436/2023-2024 | 54/CD | 10/01/2024 | 10/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 44.63 | 42.34 | 94.88 | 100
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Sinking of Big Dia Tubewell at HWSite & 2nd Site of KALARAYERKUTHI ZONE ¿ II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000470/2022-2023 | 1525/CD | 20/01/2023 | 10/04/2024 | TAPAN CHANDA | 23.41 | 23.23 | 99.25 | 100
32 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Providing FHTC Laying Of Pipe Line And Construction Of Boundary Wall And Pump House At HW Site At KALARAYER KUTHE (ZONE-II) PWSS under JAL JEEVAN MISSION (Part-B2) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000469/2022-2023 | 1520/CD | 19/01/2023 | 19/04/2023 | LONGLAST PIPES (INDIA) PVT. LTD. | 95.79 | 0 | 0 | 50
33 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHTC LAYING OF PIPE LINE AT KALARAYER KUTHE (ZONE-III) PWSS under JAL JEEVAN MISSION (PART-C2) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000475/2022-2023 | 1530/CD | 20/01/2023 | 20/04/2023 | PARITOSH DUTTA | 62.76 | 62.17 | 99.07 | 45
34 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Providing FHTC Laying Of Pipe Line And Construction Of Boundary Wall And Pump House At 3rd Site At KALARAYER KUTHE (ZONE-III) PWSS under JAL JEEVAN MISSION (Part-C1) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000482/2022-2023 | 1537/CD | 20/01/2023 | 20/04/2023 | SANKAR BANIK | 81.88 | 77.64 | 94.81 | 94
35 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Providing FHTC Laying Of Pipe Line And Construction Of Boundary Wall And Pump House At HW Site At KALARAYER KUTHE (ZONE-III) PWSS under JAL JEEVAN MISSION (Part-B1) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000476/2022-2023 | 1531/CD | 20/01/2023 | 20/04/2023 | SUSHANTA SAHA | 59.98 | 44.33 | 73.91 | 36
36 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHTC LAYING OF PIPE LINE AT KALARAYER KUTHE (ZONE-I) PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000479/2022-2023 | 1534/CD | 20/01/2023 | 20/04/2023 | SANKAR CHAKRABORTY | 71.14 | 65.68 | 92.33 | 26
37 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHCT AT KALARAYER KUTHI PWSS |  |  | BILL/02008/2023-2024 | BP-1396 | 31/03/2024 |  | ASHIT KUMAR SINGHA | 3.04 | 0 | 0 | 0
38 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR KALARAYERKUTHI ZONE-II, PH-I |  |  | BILL/00196/2024-2025 | BP-50/24-25 | 29/04/2024 |  | WBSEDCL | 5.87 | 0 | 0 | null
39 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR KALARAYERKUTHI Z-II, PH-II |  |  | BILL/00195/2024-2025 | BP-51/24-25 | 29/04/2024 |  | WBSEDCL | 12.99 | 0 | 0 | null
40 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR KALARAYERKUTHI Z-II, PH-II |  |  | BILL/00195/2024-2025 | BP-51/24-25 | 29/04/2024 |  | WBSEDCL | 12.99 | 0 | 0 | null
41 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | PROVIDING FHTC LAYING OF PIPE LINE AT KALARAYER KUTHE (ZONE-I) PWSS under JAL JEEVAN MISSION (PART ¿C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000472/2022-2023 | 1527/CD | 20/01/2023 | 20/04/2023 | ASHIT KUMAR GHOSH | 51.9 | 10.93 | 21.07 | 20
42 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for KALARAYERKUTHI Water Supply Scheme TWNo- I,of Zone-I , TWNo- I and II,of Zone-II TWNo- I,,II and IIIof Zone-III under NMDII,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001069/2023-2024 | 2708/NMD-II | 19/09/2023 | 19/10/2023 | WEST BENGAL ENGINEERING CO. | 65.2 | 15.41 | 23.64 | 100
43 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Execution of different works related to KALARAYERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000566/2023-2024 | 606/CD | 11/03/2024 | 10/05/2024 | SANKAR BANIK | 35.63 | 0 | 0 | 20
44 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
45 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | SM/14183 | Augmentation | Execution of different works related to KALARAYERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000128/2023-2024 | 633/CD | 12/07/2023 | 09/12/2023 | M/S CLASSIC BUILDERS AND TRADERS | 498.9 | 0 | 0 | 20
Total | [13 empty] | 21556.07 | 613.62 | 2.85