## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 252/CD | 27/04/2023 |  | Resource Division | 50.94 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I,Dinhata - II | Northern Mechanical Division II | KISMAT MOKARARI PWSS | SM/14201 | New | QUOTATION FOR NSC AT KISMAT MOKARANI TW NO-I |  |  | BILL/01786/2023-2024 | BP-2023-24-353 | 27/09/2023 |  | WBSEDCL | 3.14 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - I,Dinhata - II | Northern Mechanical Division II | KISMAT MOKARARI PWSS | SM/14201 | New | QUOTATION FOR NSC AT KISMAT MOKARANI TW NO-II |  |  | BILL/01787/2023-2024 | BP-2023-24-354 | 27/09/2023 |  | WBSEDCL | 3.18 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 79/CD | 11/01/2024 |  | Resource Division | 15.22 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000465/2023-2024 | 210/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000463/2023-2024 | 208/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000464/2023-2024 | 209/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
8 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000462/2023-2024 | 207/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Execution of different works related to KISMAT MOKARARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000516/2022-2023 | 1603/CD | 03/02/2023 | 03/07/2023 | UMEX POLYMERS PVT LTD | 497.23 | 322.59 | 64.88 | 39
10 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
11 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Execution of different works related to KISMAT MOKARARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000344/2023-2024 | 1328/CD | 24/11/2023 | 23/01/2024 | KISHORE BOSE | 29.67 | 0 | 0 | 64
12 | COOCHBEHAR | Dinhata - I,Dinhata - II | Northern Mechanical Division II | KISMAT MOKARARI PWSS | SM/14201 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kismat Mokarari water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001013/2023-2024 | 2595/NMD-II | 24/08/2023 | 23/09/2023 | UTTAM PAUL | 21.01 | 0 | 0 | 80
13 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
14 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE DINHATA BOXIRHAT road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, (1) LANKABAR PIPED WATER SUPPLY SCHEME |  |  | BILL/00364/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 12.15 | 0 | 0 | 0
15 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Execution of different works related to KISMAT MOKARARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000035/2024-2025 | 1144/CD | 14/06/2024 | 13/08/2024 | GOUTAM KUMAR DAS | 70.97 | 0 | 0 | 80
16 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE Najirhat trimohini adjacent KISMAT MOKRABARI road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, |  |  | BILL/00361/2024-2025 | wr-110 | 03/09/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 22.13 | 0 | 0 | 0
17 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE DINHATA GITALDHA ADJACENT TO KISMAT MOKRABARI road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, |  |  | BILL/00367/2024-2025 | wr-110 | 03/09/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 12.05 | 0 | 0 | 0
18 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE BHETAGURI NAJIRHAT road KISMAT MOKRABARI VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, (1) LANKABAR PIPED WATER SUPPLY SCHEME |  |  | BILL/00365/2024-2025 | wr-110 | 03/09/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 15.41 | 0 | 0 | 0
19 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-A) under KISMAT MOKARARI PWSS | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000341/2024-2025 | 857/CD | 12/04/2024 | 16/04/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
20 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-C) under KISMAT MOKARARI PWSS | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000343/2024-2025 | 859/CD | 12/04/2024 | 10/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
21 | COOCHBEHAR | Dinhata - I,Dinhata - II | Coochbehar Division | KISMAT MOKARARI PWSS | SM/14201 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-B) under KISMAT MOKARARI PWSS | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000342/2024-2025 | 858/CD | 12/04/2024 | 10/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
Total | [13 empty] | 20596.78 | 326.53 | 1.59