## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | ABUAR PATHAR PWSS | SM/14202 | New | QUOTATION FOR NSC AT ABUAR PATHAR PH NO-I |  |  | BILL/01751/2023-2024 | BP-2023-24-357 | 27/09/2023 | 27/09/2023 | WBSEDCL | 9.77 | 0 | 0 | 0
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | ABUAR PATHAR PWSS | SM/14202 | New | QUOTATION FOR NSC AT ABUAR PATHAR PH NO-II |  |  | BILL/01752/2023-2024 | BP-2023-24-358 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.94 | 0 | 0 | 0
3 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | Providing FHTC & other allied works in the command area of KISMAT DASGRAM PWSS under Cooch Behar Division, PHED |  |  | ORD/000193/2024-2025 | 5008 | 18/06/2024 | 16/09/2024 | A.O BSNL | 0 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | Execution of different works related to ABUAR PATHAR PWSS under JAL JEEVAN MISSION P B | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000037/2024-2025 | 1713/CD | 25/09/2024 | 24/11/2024 | DAFFODIL | 62.53 | 0 | 0 | 0
5 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | ABUAR PATHAR PWSS | SM/14202 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Abuar Pathar water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001008/2023-2024 | 2590/NMD-II | 24/08/2023 | 23/09/2023 | CHOWDHURY AND BASU ENTERPRISE | 21.02 | 20.82 | 99.05 | 100
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 93/CD | 11/01/2024 | 11/01/2024 | Resource Division | 14.96 | 0 | 0 | 0
7 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000088/2025-2026 | z24 | 05/07/2025 | 03/10/2025 | NORTH BENGAL CONSTRUCTION CO | 37.91 | 0 | 0 | 0
8 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | Execution of different works related to ABUAR PATHAR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1335/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000593/2022-2023 | 1963/CD | 24/03/2023 | 21/08/2023 | S & P ENTERPRISE | 540.9 | 393.87 | 72.82 | 35
9 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000070/2025-2026 | 646/CD | 05/05/2025 | 03/08/2025 | Z STAR COMMOTRADE PVT LTD | 62.77 | 0 | 0 | 0
11 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | ABUAR PATHAR PWSS | SM/14202 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000283/2025-2026 | 792/CD | 23/05/2025 | 21/08/2025 | ANIMESH DHAR CHOUDHURY | 32.79 | 0 | 0 | 0
Total | [13 empty] | 20577.88 | 414.7 | 2.02