## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | ELECTRIC QUOTATION BILL FOR NSC AT ASAKBARI PRATHAM KHANDA TW II |  |  | BILL/02046/2023-2024 | BP-2023-24-441 | 05/12/2023 | 05/12/2023 | WBSEDCL | 4.32 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | ELECTRIC QUOTATION MONEY FOR NSC AT ASAKBARI PRATHAM KHANDA TW I |  |  | BILL/02045/2023-2024 | BP-2023-24-442 | 05/12/2023 | 05/12/2023 | WBSEDCL | 3.99 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 84/CD | 11/01/2024 | 11/01/2024 | Resource Division | 17.03 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Execution of different works related to ASAKBARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1241/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000583/2022-2023 | 1773/CD | 02/03/2023 | 28/01/2026 | ASHIT KUMAR SINGHA | 504.05 | 341.84 | 67.82 | 75
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 135.01 | 0.68 | 20
6 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Execution of different works related to ASAKBARI PRATHAM KHANDA and SHIKARPUR PWSS under JAL JEEVAN MISSION MTB |  |  | ORD/000606/2023-2024 | 652/CD | 11/03/2024 | 10/05/2024 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 25.02 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000059/2025-2026 | 695/CD | 16/05/2025 | 12/11/2025 | M/S JAYA SARKAR | 12.09 | 0 | 0 | 65
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000105/2025-2026 | 1425/CD | 11/08/2025 | 09/11/2025 | SENGUPTA ENTERPRISE | 42.84 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Execution of different works related to CHONGERKHATA KHAGRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000549/2022-2023 | 1683/CD | 13/02/2023 | 07/01/2026 | BIJOY ROY | 92.22 | 45.92 | 49.79 | 95
10 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Asakbari Pratham Khanda water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001023/2023-2024 | 2597/NMD-II | 24/08/2023 | 06/03/2025 | M/S CHANDRANATH MUKHERJEE | 21.84 | 17.87 | 81.82 | 100
11 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Execution of different works related to ASAKBARI P KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000396/2023-2024 | 1368/CD | 05/12/2023 | 08/04/2025 | ASHIT KUMAR SINGHA | 96.83 | 0 | 0 | 50
12 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II, ASAKBARI PRATHAM KHANDA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000642/2024-2025 | 1857/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
13 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi, ASAKBARI PRATHAM KHANDA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000645/2024-2025 | 1859/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
14 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I, ASAKBARI PRATHAM KHANDA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000641/2024-2025 | 1856/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
15 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai, ASAKBARI PRATHAM KHANDA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000644/2024-2025 | 1858/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
16 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | ASAKBARI PRATHAM KHANDA PWSS | SM/14203 | New | Providing Sanitary and Water Supply Arrangement to the Temporary Establishment for the accommodation of CAPF & SPF in connection with West Bengal Legislative Assembly Election 2026 Venue ID |  |  | ORD/000067/2026-2027 | 20062 | 30/04/2026 | 07/05/2026 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
Total | [13 empty] | 20613.47 | 544.58 | 2.64