## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | Execution of different works related to DAKSHIN KHARIJA GITALDAHA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000518/2022-2023 | 1605/CD | 03/02/2023 | 15/10/2026 | UMEX POLYMERS PVT LTD | 412.2 | 323.19 | 78.41 | 32
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Dakshin Kharija Gitaldaha water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001012/2023-2024 | 2594/NMD-II | 24/08/2023 | 01/03/2025 | SUMON ELECTRICAL | 21.02 | 17.04 | 81.08 | 100
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
4 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | WALL PAINTING DESIGNING MAKING & ERECTING OF DB USING LOGO TAGLINE FOR COOCHBEHAR DISTRICT UNDER JJAM SUPPORT ACTIVITIES. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000621/2024-2025 | 2322/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 86.56 | 0 | 0 | 100
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 77/CD | 11/01/2024 | 11/01/2024 | Resource Division | 15.21 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | Charges for new service connection at Dakshin Kharija Gitaldaha PWSS, P/H-I. |  |  | BILL/00748/2024-2025 | BP-207/24-25 | 24/07/2024 | 24/07/2024 | WBSEDCL | 8.68 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | Charges for new service connection at Dakshin kharija gitaldaha PWSS, P/H-II |  |  | BILL/00749/2024-2025 | BP-206/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 5.02 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 07/08/2026 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKSHIN KHARIJA GITALDAHA PWSS | SM/14204 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000086/2025-2026 | 734/CD | 17/05/2025 | 15/08/2025 | M/S SURAJIT MAJUMDER | 33.76 | 0 | 0 | 30
Total | [13 empty] | 20439.26 | 340.24 | 1.66