## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | INDRA NARAYAN PWSS | SM/14205 | New | QUOTATION FOR NSC AT INDRANARAYAN PH NO-II |  |  | BILL/01757/2023-2024 | BP-2023-24-333 | 03/10/2023 | 03/10/2023 | WBSEDCL | 5.85 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | INDRA NARAYAN PWSS | SM/14205 | New | QUOTATION FOR NSC AT INDRANARAYAN PH NO-I |  |  | BILL/01756/2023-2024 | BP-2023-24-332 | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.15 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Name of Work: Execution of different works related to INDRA NARAYAN PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000266/2023-2024 | 1033/CD | 22/09/2023 | 21/12/2023 | GOUTAM KUMAR DAS | 38.47 | 30.74 | 79.91 | 80
4 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | EXECUTION OF DIFFERENT WORKS RELATED TO INDRA NARAYAN AND BARA PHALIMARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000524/2024-2025 | 2019 | 23/12/2024 | 21/02/2025 | KAJAL KUMAR DE | 61.67 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000458/2023-2024 | 203/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000460/2023-2024 | 205/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000461/2023-2024 | 206/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000459/2023-2024 | 204/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | RAGISTRATION OF LAND |  |  | BILL/00592/2024-2025 | BP-228 | 01/08/2024 | 01/08/2024 | SWAPAN KR.SARKAR | 0.84 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Execution of different works related to INDRA NARAYAN PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000515/2022-2023 | 1602/CD | 03/02/2023 | 03/07/2023 | UMEX POLYMERS PVT LTD | 336.07 | 321.37 | 95.63 | 100
11 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
12 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000018/2025-2026 | 703/CD | 17/05/2025 | 15/08/2025 | UMEX POLYMERS PVT LTD | 42.05 | 0 | 0 | 0
13 | COOCHBEHAR | Dinhata-I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000130/2025-2026 | 603/CD | 28/04/2025 | 27/07/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
Total | [13 empty] | 20379.15 | 356.05 | 1.75