## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | INDRA NARAYAN PWSS | SM/14205 | New | QUOTATION FOR NSC AT INDRANARAYAN PH NO-I |  |  | BILL/01756/2023-2024 | BP-2023-24-332 | 27/09/2023 |  | WBSEDCL | 4.15 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | INDRA NARAYAN PWSS | SM/14205 | New | QUOTATION FOR NSC AT INDRANARAYAN PH NO-II |  |  | BILL/01757/2023-2024 | BP-2023-24-333 | 03/10/2023 |  | WBSEDCL | 5.85 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Name of Work: Execution of different works related to INDRA NARAYAN PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000266/2023-2024 | 1033/CD | 22/09/2023 | 21/12/2023 | GOUTAM KUMAR DAS | 38.47 | 15.37 | 39.96 | 80
4 | COOCHBEHAR | Dinhata - I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000458/2023-2024 | 203/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
5 | COOCHBEHAR | Dinhata - I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000460/2023-2024 | 205/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Dinhata - I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000461/2023-2024 | 206/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR | Dinhata - I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II Water Supply Scheme under Cooch Behar Division, PHED. |  | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000459/2023-2024 | 204/CD | 05/02/2024 | 05/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
8 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | INDRA NARAYAN PWSS | SM/14205 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Indra Narayan water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001016/2023-2024 | 2599/NMD-II | 24/08/2023 | 23/09/2023 | SUDIP DUTTA | 18.54 | 6.9 | 37.22 | 60
9 | COOCHBEHAR | Dinhata - I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata - I | Coochbehar Division | INDRA NARAYAN PWSS | SM/14205 | New | Execution of different works related to INDRA NARAYAN PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000515/2022-2023 | 1602/CD | 03/02/2023 | 03/07/2023 | UMEX POLYMERS PVT LTD | 336.07 | 215 | 63.97 | 50
Total | [13 empty] | 20196.31 | 241.21 | 1.19