## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 245/CD | 27/04/2023 | 27/04/2023 | Resource Division | 25.11 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | ELECTRIC QUOTATION BILL FOR NSC AT DHANDHANIA TW II |  |  | BILL/02049/2023-2024 | BP-2023-24-439 | 05/12/2023 | 05/12/2023 | WBSEDCL | 4.81 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 83/CD | 11/01/2024 | 11/01/2024 | Resource Division | 13.2 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | FUEL BILL |  |  | BILL/02056/2023-2024 | BP-1415 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.41 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | ELECTRIC QUOTATION FOR NSC AT DHANDHANIA TW I |  |  | BILL/02048/2023-2024 | BP-2023-24-440 | 05/12/2023 | 05/12/2023 | WBSEDCL | 4.81 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | HIRING VEHICLE FOR AE/HQ |  |  | BILL/00535/2024-2025 | BP-217 | 31/07/2024 | 31/07/2024 | ANIMESH DHAR CHOUDHURY | 0.73 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | Execution of different works related to DHANDHANIA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000379/2023-2024 | 1363/CD | 05/12/2023 | 28/01/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 91.66 | 0 | 0 | 55
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000054/2025-2026 | 602/CD | 28/04/2025 | 27/07/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | Execution of different works related to DHANDHANIA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1238/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000602/2022-2023 | 1791/CD | 02/03/2023 | 21/03/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 578.5 | 0 | 0 | 93
11 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | DHAN DHANIA & ITS ADJOINING MOUZAS PWSS | SM/14206 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Dhandhania water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001015/2023-2024 | 2598/NMD-II | 24/08/2023 | 01/01/2025 | TALUKDAR ENTERPRISE | 21.02 | 0 | 0 | 100
Total | [13 empty] | 20627.35 | 0 | 0