## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC and Laying of Pipe line at ATPUKURI ZONE ¿I PWSS under JAL JEEVAN MISSION (PART ¿E) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000736/2022-2023 | 1734/CD | 21/02/2023 | 22/04/2023 | ASHIM KUMAR CHAKRABORTY | 81.56 | 72.1 | 88.4 | 1
2 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXC. OF DIFFT. WORK AT SITAI ZONE-I PWSS |  |  | BILL/00690/2023-2024 | BP-349 | 20/07/2023 | 20/07/2023 | PALLAB BHAWAL | 31.9 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC & Construction of pump house, Boundary wall (HW site) and laying of Pipe line other allied works at ATPUKURI ZONE - II PWSS Under Cooch Behar division P.H.E.Dte.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000731/2022-2023 | 1739/CD | 21/02/2023 | 22/04/2023 | GEETA CONSTRUCTION | 96.66 | 82.2 | 85.04 | 85
4 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC & Construction of Pumphouse at HWSite and laying of Pipe line and other allied works at ATPUKURI ZONE - I PWSS Under Cooch Behar division P.H.E.Dte.(Part-F) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000733/2022-2023 | 1737/CD | 21/02/2023 | 22/04/2023 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 82.37 | 16.95 | 20.58 | 75
5 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION ZI PART J2 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000133/2023-2024 | 729/CD | 26/07/2023 | 24/09/2023 | KARTICK CH SEAL | 97.66 | 79.92 | 81.83 | 82
6 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI Z 2 PWSS under JAL JEEVAN MISSION B | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000008/2024-2025 | 1157/CD | 14/06/2024 | 11/12/2024 | M/S. SAHA CONSTRUCTION | 41.56 | 6.16 | 14.83 | 100
7 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI Z1 PWSS under JAL JEEVAN MISSION B |  |  | ORD/000057/2024-2025 | 1336/CD | 24/07/2024 | 22/10/2024 | NARENDRA BHADANI | 30.95 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within Atpukhari area) BHERBHERI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000610/2024-2025 | 2311/CD | 23/12/2024 | 21/02/2025 | SHREE RANI SATI ENTERPRISE | 42.11 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Supply of different Forms & Stationary Items for day to day Office work for the Office of the Assistant Engineer, RWS Cooch Behar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000055/2023-2024 | 268/CD | 28/04/2023 | 05/05/2023 | EASTERN MARKETING ENTERPRISE | 0.98 | 0.98 | 100 | 100
10 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Sinking of Big Dia Tubewell works related to ATPUKURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000784/2022-2023 | 1860/CD | 14/03/2023 | 13/04/2023 | MS DD ENTERPRISE | 52.86 | 0 | 0 | 100
11 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under ATPUKHARI Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000500/2024-2025 | 1025/CD | 03/05/2024 | 17/06/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
12 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under ATPUKHARI Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000499/2024-2025 | 1005/CD | 30/04/2024 | 14/06/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
13 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under ATPUKHARI Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000501/2024-2025 | 1026/CD | 06/05/2024 | 20/06/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
14 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under ATPUKHARI Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. (Part-D) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000502/2024-2025 | 1047/CD | 14/05/2024 | 06/11/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
15 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-II, TW-II. |  |  | BILL/02758/2023-2024 | BP-2023-24-628 | 22/02/2024 | 22/02/2024 | WBSEDCL | 9.1 | 0 | 0 | 0
16 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW II |  |  | BILL/02760/2023-2024 | BP-2023-24-633 | 22/02/2024 | 22/02/2024 | WBSEDCL | 3.88 | 0 | 0 | 0
17 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-II, TW-I. |  |  | BILL/02757/2023-2024 | BP-2023-24-627 | 22/02/2024 | 22/02/2024 | WBSEDCL | 10.26 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW III. |  |  | BILL/00827/2024-2025 | BP-255/24-25 | 08/08/2024 | 08/08/2024 | WBSEDCL | 5.6 | 0 | 0 | 0
19 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW I |  |  | BILL/02759/2023-2024 | BP-2023-24-629 | 22/02/2024 | 22/02/2024 | WBSEDCL | 7.37 | 0 | 0 | 0
20 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
21 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC & Construction of pump house, Boundary wall (2nd t/w site) and laying of Pipe line other allied works at ATPUKURI ZONE - II PWSS Under Cooch Behar division P.H.E.Dte.(Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000732/2022-2023 | 1738/CD | 21/02/2023 | 02/01/2026 | SIDHARTHA ROY | 64.52 | 57.36 | 88.91 | 100
22 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC and Laying of Pipe line & Construction of B/Wall HW Site of ATPUKURI ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000734/2022-2023 | 1736/CD | 21/02/2023 | 30/06/2025 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 82.23 | 49.24 | 59.88 | 15
23 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC and Laying of pipe line, Const. Of Pump house , B/Wall at 3rd T/W site and other allied work of ATPUKURI ZONE ¿I PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000735/2022-2023 | 1735/CD | 21/02/2023 | 01/09/2025 | ASHIM KUMAR CHAKRABORTY | 94.06 | 60.62 | 64.44 | 70
24 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000520/2022-2023 | 1607/CD | 03/02/2023 | 04/05/2025 | M/S VINOD KUMAR JAIN | 312.26 | 203.2 | 65.07 | 33
25 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Atpukhari Water Supply Scheme TW No.-I,IIandIII of Zone-I and T.W NoI and II of Zone-II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001147/2023-2024 | 2900/NMD-II | 19/10/2023 | 01/09/2025 | M/S SAJAHAN CHOWDHURY | 52.31 | 43.38 | 82.94 | 70
26 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION Z1 A | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000023/2024-2025 | 1131/CD | 14/06/2024 | 08/08/2025 | M/S VINOD KUMAR JAIN | 75.24 | 29.02 | 38.57 | 30
27 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
28 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION Z2 A | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000038/2024-2025 | 1146/CD | 14/06/2024 | 08/10/2025 | M/S VINOD KUMAR JAIN | 84.8 | 20.71 | 24.42 | 30
29 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXECUTION OF DIFFERENT WORKS RELATED TO Atpukhari & BALASUNDAR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000534/2024-2025 | 2218/CD | 23/12/2024 | 24/12/2025 | GOUTAM KUMAR DAS | 46.33 | 0 | 0 | 30
30 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000085/2025-2026 | 726/CD | 17/05/2025 | 15/08/2025 | M/S. SAHA CONSTRUCTION | 31.42 | 0 | 0 | 0
31 | COOCHBEHAR | Cooch Behar-I,Mathabhanga-II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000102/2025-2026 | 749/CD | 17/05/2025 | 15/08/2025 | TAPU BANIK | 23.04 | 0 | 0 | 0
Total | [13 empty] | 21364.02 | 725.73 | 3.4