## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC and Laying of Pipe line at ATPUKURI ZONE ¿I PWSS under JAL JEEVAN MISSION (PART ¿E) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000736/2022-2023 | 1734/CD | 21/02/2023 | 22/04/2023 | ASHIM KUMAR CHAKRABORTY | 81.56 | 72.1 | 88.4 | 1
2 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC and Laying of Pipe line & Construction of B/Wall HW Site of ATPUKURI ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000734/2022-2023 | 1736/CD | 21/02/2023 | 22/04/2023 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 82.23 | 49.24 | 59.88 | 15
3 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXC. OF DIFFT. WORK AT SITAI ZONE-I PWSS |  |  | BILL/00690/2023-2024 | BP-349 | 20/07/2023 |  | PALLAB BHAWAL | 31.9 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Supply of different Forms & Stationary Items for day to day Office work for the Office of the Assistant Engineer, RWS Cooch Behar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000055/2023-2024 | 268/CD | 28/04/2023 | 05/05/2023 | EASTERN MARKETING ENTERPRISE | 0.98 | 0.98 | 100 | 100
5 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION ZI PART J2 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000133/2023-2024 | 729/CD | 26/07/2023 | 24/09/2023 | KARTICK CH SEAL | 97.66 | 30.29 | 31.01 | 82
6 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-II, TW-I. |  |  | BILL/02757/2023-2024 | BP-2023-24-627 | 22/02/2024 |  | WBSEDCL | 10.26 | 0 | 0 | null
7 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW I |  |  | BILL/02759/2023-2024 | BP-2023-24-629 | 22/02/2024 |  | WBSEDCL | 7.37 | 0 | 0 | null
8 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW I |  |  | BILL/02759/2023-2024 | BP-2023-24-629 | 22/02/2024 |  | WBSEDCL | 7.37 | 0 | 0 | null
9 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-II, TW-II. |  |  | BILL/02758/2023-2024 | BP-2023-24-628 | 22/02/2024 |  | WBSEDCL | 9.1 | 0 | 0 | null
10 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Sinking of Big Dia Tubewell works related to ATPUKURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000784/2022-2023 | 1860/CD | 14/03/2023 | 13/04/2023 | MS DD ENTERPRISE | 52.86 | 0 | 0 | 100
11 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Atpukhari Water Supply Scheme TW No.-I,IIandIII of Zone-I and T.W NoI and II of Zone-II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001147/2023-2024 | 2900/NMD-II | 19/10/2023 | 18/11/2023 | M/S SAJAHAN CHOWDHURY | 52.31 | 21.69 | 41.47 | 50
12 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | FUEL BILL |  |  | BILL/02025/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 2.06 | 0 | 0 | 0
13 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 |  | MALAY KR.DEB | 109.82 | 0 | 0 | 0
14 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000520/2022-2023 | 1607/CD | 03/02/2023 | 03/07/2023 | M/S VINOD KUMAR JAIN | 312.26 | 64.83 | 20.76 | 33
15 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC & Construction of pump house, Boundary wall (2nd t/w site) and laying of Pipe line other allied works at ATPUKURI ZONE - II PWSS Under Cooch Behar division P.H.E.Dte.(Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000732/2022-2023 | 1738/CD | 21/02/2023 | 22/04/2023 | SIDHARTHA ROY | 64.52 | 34.92 | 54.12 | 85
16 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC & Construction of pump house, Boundary wall (HW site) and laying of Pipe line other allied works at ATPUKURI ZONE - II PWSS Under Cooch Behar division P.H.E.Dte.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000731/2022-2023 | 1739/CD | 21/02/2023 | 22/04/2023 | GEETA CONSTRUCTION | 96.66 | 60.27 | 62.35 | 85
17 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI Z 2 PWSS under JAL JEEVAN MISSION B | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000008/2024-2025 | 1157/CD | 14/06/2024 | 13/08/2024 | M/S. SAHA CONSTRUCTION | 41.56 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC & Construction of Pumphouse at HWSite and laying of Pipe line and other allied works at ATPUKURI ZONE - I PWSS Under Cooch Behar division P.H.E.Dte.(Part-F) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000733/2022-2023 | 1737/CD | 21/02/2023 | 22/04/2023 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 82.37 | 0 | 0 | 75
19 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW II |  |  | BILL/02760/2023-2024 | BP-2023-24-633 | 22/02/2024 |  | WBSEDCL | 3.88 | 0 | 0 | null
20 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW II |  |  | BILL/02760/2023-2024 | BP-2023-24-633 | 22/02/2024 |  | WBSEDCL | 3.88 | 0 | 0 | null
21 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI Z1 PWSS under JAL JEEVAN MISSION B |  |  | ORD/000057/2024-2025 | 1336/CD | 24/07/2024 | 22/10/2024 | NARENDRA BHADANI | 30.95 | 0 | 0 | 0
22 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
23 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Providing FHTC and Laying of pipe line, Const. Of Pump house , B/Wall at 3rd T/W site and other allied work of ATPUKURI ZONE ¿I PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000735/2022-2023 | 1735/CD | 21/02/2023 | 22/04/2023 | ASHIM KUMAR CHAKRABORTY | 94.06 | 45.46 | 48.33 | 70
24 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION Z2 A | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000038/2024-2025 | 1146/CD | 14/06/2024 | 13/08/2024 | M/S VINOD KUMAR JAIN | 84.8 | 0 | 0 | 30
25 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Coochbehar Division | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | Execution of different works related to ATPUKURI PWSS under JAL JEEVAN MISSION Z1 A | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000023/2024-2025 | 1131/CD | 14/06/2024 | 13/08/2024 | M/S VINOD KUMAR JAIN | 75.24 | 0 | 0 | 30
26 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW III. |  |  | BILL/00827/2024-2025 | BP-255/24-25 | 08/08/2024 |  | WBSEDCL | 5.6 | 0 | 0 | null
27 | COOCHBEHAR | Cooch Behar - I,Mathabhanga - II | Northern Mechanical Division II | Atpukhari Piped Water Supply Scheme. | SM/14250 | New | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT ATPUKRI PWSS ZONE-I TW III. |  |  | BILL/00827/2024-2025 | BP-255/24-25 | 08/08/2024 |  | WBSEDCL | 5.6 | 0 | 0 | null
Total | [13 empty] | 21236.17 | 379.78 | 1.79