## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Execution of different works related to JHURIPARA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1058/1-5/NBC-1; Dt.: 03-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000624/2022-2023 | 1614/CD | 03/02/2023 | 25/09/2026 | M/S J C ENTERPRISE | 402.48 | 356.15 | 88.49 | 80
2 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Execution of different works related to JHURIPARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000427/2023-2024 | 1483/CD | 20/12/2023 | 28/08/2026 | M/S J C ENTERPRISE | 53.1 | 31.66 | 59.62 | 80
3 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jhuripara water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000662/2023-2024 | 1955/NMD-II | 24/07/2023 | 23/08/2023 | ANUP BASU | 21.06 | 5.09 | 24.16 | 100
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | QUOTATION FOR NSC AT JHURIPARA PH NO-I |  |  | BILL/01039/2023-2024 | BP-2023-24-236 | 27/07/2023 | 27/07/2023 | WBSEDCL | 4.02 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | QUOTATION FOR NSC AT JHURIPARA PH NO-II |  |  | BILL/01038/2023-2024 | BP-2023-24-237 | 27/07/2023 | 27/07/2023 | WBSEDCL | 6.97 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | EXECUTION OF DIFFERENT WORKS RELATED TO JHURIPARA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000516/2024-2025 | 2293/CD | 23/12/2024 | 16/06/2026 | M/S J C ENTERPRISE | 41.12 | 0 | 0 | 90
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | HORDING/ SIGN BOARD FOR IEC CAMPAINING AT GP OFFICE / BLOCK OFFICE & DIFFERENT HEALTH CENTERS UNDER COOCH BEHAR DIVISION , PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000704/2024-2025 | 2326/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 48.03 | 0 | 0 | 100
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
Total | [13 empty] | 20413.63 | 392.9 | 1.92