## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jhuripara water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000662/2023-2024 | 1955/NMD-II | 24/07/2023 | 23/08/2023 | ANUP BASU | 21.06 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | QUOTATION FOR NSC AT JHURIPARA PH NO-I |  |  | BILL/01039/2023-2024 | BP-2023-24-236 | 27/07/2023 |  | WBSEDCL | 4.02 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | QUOTATION FOR NSC AT JHURIPARA PH NO-II |  |  | BILL/01038/2023-2024 | BP-2023-24-237 | 27/07/2023 |  | WBSEDCL | 6.97 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Execution of different works related to JHURIPARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000427/2023-2024 | 1483/CD | 20/12/2023 | 18/02/2024 | M/S J C ENTERPRISE | 53.1 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Execution of different works related to JHURIPARA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1058/1-5/NBC-1; Dt.: 03-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000624/2022-2023 | 1614/CD | 03/02/2023 | 03/07/2023 | M/S J C ENTERPRISE | 402.48 | 213.82 | 53.12 | 80
7 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JHURIPARA PIPED WATER SUPPLY SCHEME | SM/14439 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20324.48 | 213.82 | 1.05