## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Haldibari | Coochbehar Division | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | Execution of different works related to JNANDAS PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1126/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000626/2022-2023 | 1885/CD | 14/03/2023 | 11/08/2023 | UNIBRO INFRASERV PRIVATE LIMITED | 418.79 | 158.61 | 37.87 | 25
2 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jnandas and its adjoining moujas water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001084/2023-2024 | 2780/NMD-II | 05/10/2023 | 04/11/2023 | DILIP MAHATO | 18.56 | 14.08 | 75.85 | 50
3 | COOCHBEHAR | Haldibari | Coochbehar Division | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 205/CD | 27/04/2023 | 27/04/2023 | Resource Division | 21.69 | 0 | 0 | 0
4 | COOCHBEHAR | Haldibari | Coochbehar Division | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR | Haldibari | Coochbehar Division | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | EXECUTION OF DIFFERENT WORKS RELATED TO JNANDAS & DAKSHIN BAJEJAMA KHASBAS PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000531/2024-2025 | 2215/CD | 23/12/2024 | 21/10/2025 | ASOK KUMAR DHAR | 71.16 | 0 | 0 | 30
6 | COOCHBEHAR | Haldibari | Coochbehar Division | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 80/CD | 11/01/2024 | 11/01/2024 | Resource Division | 12.42 | 0 | 0 | 0
7 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT JNANDAS PWSS TW II |  |  | BILL/02724/2023-2024 | BP-2023-24-599 | 15/02/2024 | 15/02/2024 | WBSEDCL | 5.39 | 0 | 0 | 0
8 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT JNANDAS PWSS TW I |  |  | BILL/02725/2023-2024 | BP-2023-24-598 | 15/02/2024 | 15/02/2024 | WBSEDCL | 9.66 | 0 | 0 | 0
9 | COOCHBEHAR | Haldibari | Coochbehar Division | JNANDAS & ITS ADJOINING MOUZAS PWSS | SM/14446 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000271/2025-2026 | 743/CD | 17/05/2025 | 15/08/2025 | M/S BADAL CH SAHA | 96.84 | 0 | 0 | 0
Total | [13 empty] | 20443.81 | 172.68 | 0.84