## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 250/CD | 27/04/2023 |  | Resource Division | 15.57 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHARIJA DURGANAGAR Dwitiya khanda water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000499/2023-2024 | 1762/NMD-II | 18/07/2023 | 17/08/2023 | DILIP MAHATO | 18.56 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | QUOTATION FOR NSC AT KHARIJA DURGA NAGAR TW NO-I |  |  | BILL/01805/2023-2024 | BP-2023-24-360 | 27/09/2023 |  | WBSEDCL | 3.02 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000381/2023-2024 | 1077/CD | 27/09/2023 | 26/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.49 | 50 | 100
5 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000382/2023-2024 | 1081/CD | 29/09/2023 | 28/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000380/2023-2024 | 1067/CD | 27/09/2023 | 26/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Execution of different works related to KHARIJA DURGANAGAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000424/2023-2024 | 1480/CD | 20/12/2023 | 18/02/2024 | MS SSB CONSTRUCTION CO | 80.89 | 36.96 | 45.69 | 89
8 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Charges for new service connection at Kharija durganagar 2nd khanda pwss, P/H-II. |  |  | BILL/00205/2024-2025 | BP-46/24-25 | 29/04/2024 |  | WBSEDCL | 6.32 | 0 | 0 | null
9 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Charges for new service connection at Kharija durganagar 2nd khanda pwss, P/H-II. |  |  | BILL/00205/2024-2025 | BP-46/24-25 | 29/04/2024 |  | WBSEDCL | 6.32 | 0 | 0 | null
10 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Execution of different works related to KHARIJA DURGANAGAR DWITIA KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000592/2022-2023 | 1672/CD | 13/02/2023 | 14/05/2023 | MS SSB CONSTRUCTION CO | 367.23 | 251.93 | 68.6 | 90
11 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20290.16 | 291.35 | 1.44