## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000381/2023-2024 | 1077/CD | 27/09/2023 | 27/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
2 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000382/2023-2024 | 1081/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
3 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000380/2023-2024 | 1067/CD | 27/09/2023 | 27/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
4 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 250/CD | 27/04/2023 | 27/04/2023 | Resource Division | 15.57 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | QUOTATION FOR NSC AT KHARIJA DURGA NAGAR TW NO-I |  |  | BILL/01805/2023-2024 | BP-2023-24-360 | 27/09/2023 | 27/09/2023 | WBSEDCL | 3.02 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Execution of different works related to KHARIJA DURGANAGAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000424/2023-2024 | 1480/CD | 20/12/2023 | 18/02/2024 | MS SSB CONSTRUCTION CO | 80.89 | 72.76 | 89.95 | 89
7 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Charges for new service connection at Kharija durganagar 2nd khanda pwss, P/H-II. |  |  | BILL/00205/2024-2025 | BP-46/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 6.32 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | HIRING VEHICLE FOR TFG/JE |  |  | BILL/00562/2024-2025 | BP-214 | 31/07/2024 | 31/07/2024 | GOUTAM KUMAR DAS | 0.58 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Execution of different works related to KHARIJA DURGANAGAR DWITIA KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000592/2022-2023 | 1672/CD | 13/02/2023 | 09/04/2025 | MS SSB CONSTRUCTION CO | 367.23 | 307.82 | 83.82 | 90
10 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
11 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000018/2025-2026 | 703/CD | 17/05/2025 | 15/08/2025 | UMEX POLYMERS PVT LTD | 42.05 | 0 | 0 | 0
12 | COOCHBEHAR | Dinhata-II | Coochbehar Division | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000075/2025-2026 | 752/CD | 17/05/2025 | 15/08/2025 | SHREE RANI SATI ENTERPRISE | 56.67 | 0 | 0 | 0
13 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | KHARIJA DURGANAGAR DWITIYA KHANDA PWSS | SM/14449 | New | Making of board depicting the technical data & others at Baishguri khanda & other adjacent PWSS within the Dinhata-I & II Block in the district of Cooch Behar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000870/2025-2026 | 1158/CMSD | 12/09/2025 | 22/09/2025 | DIAMOND ELECTRICAL WORKS | 0.93 | 0 | 0 | 0
Total | [13 empty] | 20365.5 | 383.54 | 1.88