## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Execution of different works related to UTTAR SINGIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000047/2023-2024 | 407/CD | 23/05/2023 | 20/10/2023 | SANKAR CHAKRABORTY | 313.93 | 63.91 | 20.36 | 40
2 | COOCHBEHAR | Sitai | Northern Mechanical Division II | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION CONNECTION AT UTTAR SINGIMARI TW I |  |  | BILL/00048/2024-2025 | BP-08/24-25 | 08/04/2024 |  | WBSEDCL | 4.05 | 0 | 0 | null
3 | COOCHBEHAR | Sitai | Northern Mechanical Division II | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT UTTAR SINGIMARI TW II. |  |  | BILL/00049/2024-2025 | BP-07/24-25 | 08/04/2024 |  | WBSEDCL | 4.77 | 0 | 0 | null
4 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000333/2024-2025 | 851/CD | 12/04/2024 | 10/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
5 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000335/2024-2025 | 853/CD | 12/04/2024 | 10/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
6 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-II, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000336/2024-2025 | 854/CD | 12/04/2024 | 10/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
7 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000334/2024-2025 | 852/CD | 12/04/2024 | 10/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
8 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Haldibari, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000338/2024-2025 | 856/CD | 12/04/2024 | 10/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
9 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mekhliganj, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000337/2024-2025 | 855/CD | 12/04/2024 | 10/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
10 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
11 | COOCHBEHAR | Sitai | Northern Mechanical Division II | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR SINGIMARI water supply scheme, TW no- I and II Under JJM under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/002041/2023-2024 | 1191/NMD-II | 11/03/2024 | 10/04/2024 | SUMON ELECTRICAL | 21.77 | 10.27 | 47.18 | 100
Total | [13 empty] | 20139.72 | 74.18 | 0.37