## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Execution of different works related to UTTAR SINGIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000047/2023-2024 | 407/CD | 23/05/2023 | 20/11/2025 | SANKAR CHAKRABORTY | 313.93 | 167.93 | 53.49 | 95
2 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
3 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | FABRICATION AND INSTALLATION OF LAND POSSESSION SIGN BOARD AT EVERY LANDS OF DIFFERENT PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000623/2024-2025 | 2325/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 44.29 | 0 | 0 | 100
4 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000333/2024-2025 | 851/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
5 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000334/2024-2025 | 852/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mekhliganj, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000337/2024-2025 | 855/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Haldibari, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000338/2024-2025 | 856/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
8 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000335/2024-2025 | 853/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-II, UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000336/2024-2025 | 854/CD | 12/04/2024 | 12/08/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
10 | COOCHBEHAR | Sitai | Northern Mechanical Division II | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR SINGIMARI water supply scheme, TW no- I and II Under JJM under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/002041/2023-2024 | 1191/NMD-II | 11/03/2024 | 10/04/2024 | SUMON ELECTRICAL | 21.77 | 21.62 | 99.3 | 100
11 | COOCHBEHAR | Sitai | Northern Mechanical Division II | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT UTTAR SINGIMARI TW II. |  |  | BILL/00049/2024-2025 | BP-07/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 4.77 | 0 | 0 | 0
12 | COOCHBEHAR | Sitai | Northern Mechanical Division II | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION CONNECTION AT UTTAR SINGIMARI TW I |  |  | BILL/00048/2024-2025 | BP-08/24-25 | 08/04/2024 | 08/04/2024 | WBSEDCL | 4.05 | 0 | 0 | 0
13 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000277/2025-2026 | 737/CD | 17/05/2025 | 12/02/2026 | SANKAR CHAKRABORTY | 39.09 | 0 | 0 | 95
14 | COOCHBEHAR | Sitai | Coochbehar Division | UTTAR SINGIMARI PIPED WATER SUPPLY SCHEME | SM/14452 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000052/2025-2026 | 723/CD | 17/05/2025 | 15/08/2025 | GOUTAM KUMAR DAS | 42.26 | 0 | 0 | 100
Total | [13 empty] | 20265.35 | 195.45 | 0.96