## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | Execution of different works related to NUTANBAS PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000517/2022-2023 | 1604/CD | 03/02/2023 | 02/04/2025 | UMEX POLYMERS PVT LTD | 411.29 | 224.87 | 54.67 | 75
2 | COOCHBEHAR | Sitai | Northern Mechanical Division II | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Natunbas water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001010/2023-2024 | 2592/NMD-II | 24/08/2023 | 04/02/2025 | M/S MATRI CONSTRUCTION | 18.5 | 5.3 | 28.65 | 100
3 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
4 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within NUTANBAS area) Gosanimari PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000617/2024-2025 | 2318/CD | 23/12/2024 | 22/04/2025 | NARAYAN CHANDRA BANIK | 14 | 0 | 0 | 98
5 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | EXECUTION OF DIFFERENT WORKS RELATED TO GABUA NUTANBAS & NAKARJAN PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000530/2024-2025 | 2214/CD | 23/12/2024 | 21/02/2025 | GOUTAM KUMAR DAS | 57.03 | 0 | 0 | 100
6 | COOCHBEHAR | Sitai | Northern Mechanical Division II | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NATUNBAS TW NO. II |  |  | BILL/03023/2023-2024 | BP-2023-24-686 | 14/03/2024 | 14/03/2024 | WBSEDCL | 5.23 | 0 | 0 | 0
7 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | shifting of H.T electric line hws natunbas |  |  | BILL/00096/2024-2025 | BP-89 | 12/06/2024 | 12/06/2024 | WBSEDCL | 2.34 | 0 | 0 | 0
8 | COOCHBEHAR | Sitai | Northern Mechanical Division II | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT NATUNBAS PWSS TW NO. I. |  |  | BILL/00054/2024-2025 | BP-54/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 5.42 | 0 | 0 | 0
9 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000016/2025-2026 | 701/CD | 17/05/2025 | 15/08/2026 | UMEX POLYMERS PVT LTD | 39.89 | 0 | 0 | 95
10 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000074/2025-2026 | 789/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 69.41 | 0 | 0 | 0
11 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000114/2025-2026 | 673/CD | 13/05/2025 | 11/08/2025 | M/S SURAJIT MAJUMDER | 6.55 | 0 | 0 | 100
12 | COOCHBEHAR | Sitai | Coochbehar Division | NUTANBAS PIPED WATER SUPPLY SCHEME | SM/14453 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000051/2025-2026 | 722/CD | 17/05/2025 | 15/08/2025 | GOUTAM KUMAR DAS | 32.95 | 0 | 0 | 100
Total | [13 empty] | 20451.88 | 230.16 | 1.13