## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 172/CD | 27/04/2023 | 27/04/2023 | Resource Division | 21.26 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Northern Mechanical Division II | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BHUTKURA PH NO-II |  |  | BILL/00566/2023-2024 | BP-2023-24-151 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Northern Mechanical Division II | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | QUOTATION FOR NSC AT BHUTKURA PH NO-I |  |  | BILL/00526/2023-2024 | BP-2023-24-150 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Execution of different works related to BHUTKURA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000513/2022-2023 | 1631/CD | 08/02/2023 | 08/07/2023 | MS SSB CONSTRUCTION CO | 451.05 | 396.25 | 87.85 | 20
5 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Northern Mechanical Division II | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhutkura water supply scheme, TW no I and II of under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000751/2023-2024 | 2293/NMD-II | 31/07/2023 | 30/08/2023 | M/S PARITOSH BHOWMICK & CO. | 21.63 | 20.13 | 93.05 | 80
6 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Execution of different works related to BHUTKURA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000514/2023-2024 | 312/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 92.92 | 90.22 | 97.09 | 49
7 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 67/CD | 11/01/2024 | 11/01/2024 | Resource Division | 12.76 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Northern Mechanical Division II | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
11 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000024/2025-2026 | 706/CD | 17/05/2025 | 18/11/2025 | MS SSB CONSTRUCTION CO | 38.34 | 0 | 0 | 30
12 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Northern Mechanical Division II | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | Solarization of grid connected pumping installation at Different PWSS at Coochbehar-II Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000136/2025-2026 | 1336/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 21.84 | 0 | 0 | 0
13 | COOCHBEHAR | Dinhata-I,Sitalkuchi | Coochbehar Division | BHUTKURA PIPED WATER SUPPLY SCHEME | SM/14730 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000130/2025-2026 | 603/CD | 28/04/2025 | 27/07/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
Total | [13 empty] | 21091.91 | 506.6 | 2.4