## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 142/CD | 27/04/2023 |  | Resource Division | 28.05 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Adabari water supply scheme, TW no I and II of under NMD-II, PHE Dte.APD |  |  | ORD/000848/2023-2024 | 2420/NMD-II | 10/08/2023 | 09/09/2023 | SUBODH KUMAR BANIK | 21.45 | 0 | 0 | 0
3 | COOCHBEHAR | Sitai | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Execution of different works related to BARA ADABARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1176/1-5/NBC-1; Dt.: 24-02-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000574/2022-2023 | 1819/CD | 06/03/2023 | 04/06/2023 | S.G ENTERPRISE | 392.44 | 252.71 | 64.4 | 60
4 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARA ADABARI TW NO. I |  |  | BILL/02616/2023-2024 | BP-2023-24-580 | 01/02/2024 |  | WBSEDCL | 4.37 | 0 | 0 | null
5 | COOCHBEHAR | Sitai | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Execution of different works related to CHHOTO GAROLJHORA PWSS under JAL JEEVAN MISSION |  |  | ORD/000482/2023-2024 | 284/CD | 09/02/2024 | 09/04/2024 | S.G ENTERPRISE | 38.53 | 0 | 0 | 0
6 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARA ADABARI TW II. |  |  | BILL/02870/2023-2024 | BP-2023-24-662 | 04/03/2024 |  | WBSEDCL | 5.13 | 0 | 0 | null
7 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARA ADABARI TW II. |  |  | BILL/02870/2023-2024 | BP-2023-24-662 | 04/03/2024 |  | WBSEDCL | 5.13 | 0 | 0 | null
8 | COOCHBEHAR | Sitai | Coochbehar Division | BARA ADABARI PIPED WATER SUPPLY SCHEME | SM/14731 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20284.39 | 252.71 | 1.25