## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Supply of S.V. & CI Special as per IS Specification for NATABARI & CHARALJANI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000610/2022-2023 | 1543/CD | 24/01/2023 | 24/04/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 21.61 | 21.56 | 99.75 | 100
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 217/CD | 27/04/2023 | 27/04/2023 | Resource Division | 36.46 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | QUOTATION FOR NSC AT CHARALJANI PH NO III |  |  | BILL/01058/2023-2024 | BP-2023-24-257 | 02/08/2023 | 02/08/2023 | WBSEDCL | 5.89 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | New service connection at Charaljani pwss. |  |  | BILL/02145/2023-2024 | BP-2023-24-482 | 12/12/2023 | 12/12/2023 | WBSEDCL | 4.9 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Pipe Line in the Command area incl. Providing House connection at CHARALJANI PWSS under Cooch Behar Division. PHE Dte. PART - B | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000060/2021-2022 | 264/CD | 06/08/2021 | 05/10/2021 | SUSHANTA SAHA | 38.32 | 19.16 | 50 | 75
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Supplimentary quotation due to modification of work root at Charaljani PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/01579/2024-2025 | BP-417/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 1.64 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Execution of different works related to CHARALJANI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1115/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000573/2022-2023 | 1684/CD | 13/02/2023 | 21/11/2025 | SHREE RANI SATI ENTERPRISE | 373.1 | 292.26 | 78.33 | 90
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for AUGUMENTATION of CHARALJANI water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000753/2023-2024 | 2232/NMD-II | 28/07/2023 | 27/08/2023 | MUSTAFI CONCERN | 21.19 | 9.95 | 46.97 | 40
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000095/2025-2026 | 736/CD | 17/05/2025 | 13/11/2025 | AASHIRBAD ENTERPRISE | 42.14 | 0 | 0 | 85
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 76/CD | 15/01/2025 | 15/01/2025 | Resource Division | 61.6 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | Charges for new service connection at Charaljani PWSS, H/W Site in the dist of Coochbehar |  |  | BILL/01578/2024-2025 | BP-416/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 5.07 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | SM/14904 | Augmentation | EXECUTION OF DIFFERENT WORKS (within CHARALJANI area) RELATED TO BALABHUT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000670/2024-2025 | 99/CD | 17/01/2025 | 12/01/2026 | M/S. MANDAL CONSTRUCTION | 27.08 | 0 | 0 | 99
Total | [13 empty] | 639 | 342.93 | 53.67