## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARA PHALIMARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/14928 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO INDRA NARAYAN AND BARA PHALIMARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000524/2024-2025 | 2019 | 23/12/2024 | 21/02/2025 | KAJAL KUMAR DE | 61.67 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARA PHALIMARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/14928 | Augmentation | Charges for new service connection at Aug of Bara phalimari PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/01886/2024-2025 | BP-437/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 5.65 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARA PHALIMARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/14928 | Augmentation | Execution of different works related to BARA PHALIMARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1114/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000575/2022-2023 | 1876/CD | 14/03/2023 | 25/03/2025 | KAJAL KUMAR DE | 144.77 | 90.16 | 62.27 | 55
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARA PHALIMARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/14928 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARA PHALIMARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | SM/14928 | Augmentation | EXECUTION OF DIFFERENT WORKS (within NAHARHAT BANDAR area) RELATED TO BARA PHALIMARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000667/2024-2025 | 96/CD | 17/01/2025 | 18/03/2025 | KAJAL KUMAR DE | 20.43 | 0 | 0 | 0
Total | [13 empty] | 20021.82 | 90.16 | 0.45