## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | NEW SERVICE CONNECTION AT TUPAMARI DEWANBAS PWSS PH-II |  |  | BILL/00760/2024-2025 | BP-229/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 6.73 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | EXECUTION OF DIFFERENT WORK AT GURIAHATI PWSS |  |  | BILL/01967/2023-2024 | BP-1084 | 22/02/2024 | 22/02/2024 | CHAKRABORTY ENTERPRISE | 29.97 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | NEW SERVICE CONNECTION AT TUPAMARI DEWANBAS PWSS PH-I |  |  | BILL/00761/2024-2025 | BP-230/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 6.04 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | EXECUTION OF DIFFERENT WORK AT BARA MADHUSUDAN PWSS |  |  | BILL/01982/2023-2024 | BP-1044-P2 | 13/02/2024 | 13/02/2024 | BRAJA GOPAL SAHA | 5.14 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | Execution of different works related to TUPAMARI DEWANBAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000120/2023-2024 | 636/CD | 12/07/2023 | 01/04/2024 | M/S DHAR ENTERPRISE | 284.01 | 0 | 0 | 30
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | Supply, installation, commissioning and trial run of electro-mechanical components along with copper wound line voltage corrector for Tupamari Dewanbas water supply scheme, TW no I and II under NMD-II, PHE Dte.APD. |  |  | ORD/001075/2023-2024 | 2765/NMD-II | 04/10/2023 | 03/11/2023 | MADHAB SAHA | 20.1 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TUPAMARI DEWANBAS SHALBARI & PASCHIM MOYAMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000549/2024-2025 | 2234/CD | 23/12/2024 | 22/04/2025 | MATARA CONSTRUCTION CO. | 51.18 | 0 | 0 | 30
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within TUPAMARI DEWANBAS & LANKABAR area) PHALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000614/2024-2025 | 2315/CD | 23/12/2024 | 21/09/2025 | TAPAN CHANDA | 72.03 | 0 | 0 | 30
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TUPAMARI DEWANBAS & DHALUABARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000565/2024-2025 | 2250/CD | 23/12/2024 | 24/06/2025 | SWAPAN KR.SARKAR | 36.62 | 0 | 0 | 50
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TUPAMARI DEWANBAS HARI BHANGA GHUGHUMARI & DUDHERKUTHI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000568/2024-2025 | 2287/CD | 23/12/2024 | 22/04/2025 | MS SSB CONSTRUCTION CO | 66.53 | 0 | 0 | 30
11 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | TUPAMARI DEWANBAS PIPED WATER SUPPLY SCHEME. | SM/14936 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000276/2025-2026 | 738/CD | 17/05/2025 | 15/08/2025 | SUBHAS CHANDRA ROY | 47.78 | 0 | 0 | 0
Total | [13 empty] | 626.12 | 0 | 0