## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | Providing House connection for KISMAT BHATRIGACHHI PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000305/2022-2023 | 914/CD | 26/09/2022 | 26/10/2022 | GHOSH AND SAHA CONSTRUCTION | 10 | 10 | 100 | 1
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DANGA Piped Water Supply Scheme. | SM/14937 | New | New service connection at Danga PWSS, P/H-I |  |  | BILL/02061/2023-2024 | BP-2023-24-438 | 05/12/2023 | 05/12/2023 | WBSEDCL | 16.38 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DANGA Piped Water Supply Scheme. | SM/14937 | New | New service connection at Danga pwss, P/H-II |  |  | BILL/02059/2023-2024 | BP-2023-24-425 | 05/12/2023 | 05/12/2023 | WBSEDCL | 4.2 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | Execution of different works related to DANGA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1339/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000595/2022-2023 | 100000/CD | 24/03/2023 | 20/09/2023 | MESSRS A.B.G CONSTRUCTION | 0 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DANGA Piped Water Supply Scheme. | SM/14937 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DANGA water supply scheme, TW no I and II of Zone-I and TW no I and II of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000809/2023-2024 | 2381/NMD-II | 09/08/2023 | 01/09/2025 | M/S B ENTERPRISE | 41 | 16.35 | 39.88 | 40
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | Execution of different works related to DANGA PWSS under JAL JEEVAN MISSION P3 |  |  | ORD/000054/2024-2025 | 1268/CD | 02/07/2024 | 30/09/2024 | BILTU DAS | 39.53 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | Execution of different works related to DANGA PWSS under JAL JEEVAN MISSION P2 |  |  | ORD/000053/2024-2025 | 1267/CD | 02/07/2024 | 30/09/2024 | BILTU DAS | 69.65 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 74/CD | 11/01/2024 | 11/01/2024 | Resource Division | 18.04 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | Execution of different works related to DANGA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1339/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000584/2022-2023 | 1967/CD | 24/03/2023 | 09/09/2025 | MESSRS A.B.G CONSTRUCTION | 596.04 | 252.76 | 42.41 | 65
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
11 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DANGA Piped Water Supply Scheme. | SM/14937 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000750/2024-2025 | 2272/CD | 23/12/2024 | 21/02/2025 | NORTH BENGAL CONSTRUCTION CO | 9.09 | 0 | 0 | 50
Total | [13 empty] | 20593.21 | 279.11 | 1.36