## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | HOKADAHA PRATHAM KHANDA PWSS | SM/14938 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for HOKADAHA PRATHAM KHANDA water supply scheme, TW no I and II under JJM under NMD-II, PHE Dte. APD. |  |  | ORD/000860/2023-2024 | 2443/NMD-II | 11/08/2023 | 10/09/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.67 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | HOKADAHA PRATHAM KHANDA PWSS | SM/14938 | New | QUOTATION FOR NSC AT HOKADANGA TW NO I |  |  | BILL/02458/2023-2024 | null | 16/01/2024 |  | WBSEDCL | 9.26 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | HOKADAHA PRATHAM KHANDA PWSS | SM/14938 | New | New service connection at Hokadaha pratham khanda PWSS, P/H-I |  |  | BILL/02320/2023-2024 | BP-2023-24-533 | 17/01/2024 |  | WBSEDCL | 9.26 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - II | Coochbehar Division | HOKADAHA PRATHAM KHANDA PWSS | SM/14938 | New | Execution of different works related to HOKADAHA P. KHANDA PWSS under JAL JEEVAN MISSION |  |  | ORD/000475/2023-2024 | 277/CD | 09/02/2024 | 09/04/2024 | D S CONSTRUCTION | 83.97 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - II | Coochbehar Division | HOKADAHA PRATHAM KHANDA PWSS | SM/14938 | New | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 |  | MALAY KR.DEB | 109.82 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | HOKADAHA PRATHAM KHANDA PWSS | SM/14938 | New | Charges for new service coonection at Hokadaha pratham khanda PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/00990/2024-2025 | null | 14/08/2024 |  | WBSEDCL | 8.07 | 0 | 0 | null
7 | COOCHBEHAR | Dinhata - II | Coochbehar Division | HOKADAHA PRATHAM KHANDA PWSS | SM/14938 | New | Execution of different works related to HOKADAHA PRATHAM KHANDA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1111/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000569/2022-2023 | 1687/CD | 13/02/2023 | 13/07/2023 | D S CONSTRUCTION | 303.36 | 80 | 26.37 | 35
Total | [13 empty] | 542.42 | 80 | 14.75