## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Daribash Pratham Khanda | SM/14948 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 153/CD | 27/04/2023 | 27/04/2023 | Resource Division | 44.54 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Daribash Pratham Khanda | SM/14948 | New | Execution of different works related to BHANGRI P KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000537/2023-2024 | 325/CD | 09/02/2024 | 08/06/2024 | M/S. SAHA CONSTRUCTION | 37.21 | 29.32 | 78.8 | 79
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Daribash Pratham Khanda | SM/14948 | New | EXECUTION OF DIFFERENT WORKS RELATED TO NIGAMNAGAR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000620/2024-2025 | 2321/CD | 23/12/2024 | 21/02/2025 | TAPAN CHANDA | 96.52 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Daribash Pratham Khanda | SM/14948 | New | Charges for new service connection at Daribash pratham khanda PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/02026/2024-2025 | BP-448/24-25 | 17/12/2024 | 17/12/2024 | WBSEDCL | 4.12 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Daribash Pratham Khanda | SM/14948 | New | Charges for new service connection at Daribash pratham khanda PWSS,P/H-I in the dist of Coochbehar. |  |  | BILL/02027/2024-2025 | BP-449/24-25 | 17/12/2024 | 17/12/2024 | WBSEDCL | 3.91 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Daribash Pratham Khanda | SM/14948 | New | Execution of different works related to DARIBASH PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000437/2023-2024 | 1414/CD | 06/12/2023 | 28/07/2025 | MS HOSSEN ELECTRICALS | 300.1 | 230.17 | 76.7 | 30
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Daribash Pratham Khanda | SM/14948 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Daribash Pratham Khanda | SM/14948 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Daribash Prathm Khanda Water Supply Scheme TW No.-I ,II and III under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001094/2024-2025 | 689/NMD-II | 07/02/2025 | 09/03/2025 | DIAMOND ELECTRICAL WORKS | 31.84 | 0 | 0 | 80
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Daribash Pratham Khanda | SM/14948 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000083/2025-2026 | 725/CD | 17/05/2025 | 15/08/2025 | MS HOSSEN ELECTRICALS | 31.08 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Daribash Pratham Khanda | SM/14948 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000084/2025-2026 | 730/CD | 17/05/2025 | 15/08/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
Total | [13 empty] | 20435.43 | 259.49 | 1.27