## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Execution of different works related to BHALKA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000223/2023-2024 | 397/CD. | 23/05/2023 | 20/10/2023 | NABIN DEBNATH | 361.86 | 318.3 | 87.96 | 75
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bhalka Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001049/2023-2024 | 2699/NMD-II | 15/09/2023 | 15/10/2023 | TAPAN BISWAS | 20.11 | 19.95 | 99.22 | 100
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Execution of different works related to BHALKA area related to Baro Soulmari PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000301/2023-2024 | 1055/CD | 22/09/2023 | 20/03/2025 | NABIN DEBNATH | 41.27 | 41.19 | 99.81 | 79
4 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 155/CD | 27/04/2023 | 27/04/2023 | Resource Division | 10.62 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BHALKA PWSS TW NO -II |  |  | BILL/01423/2023-2024 | BP-2023-24-279 | 18/08/2023 | 18/08/2023 | WBSEDCL | 1.99 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BHALKA PWSS TW NO -I |  |  | BILL/01425/2023-2024 | BP-2023-24-278 | 18/08/2023 | 18/08/2023 | WBSEDCL | 4.27 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | EXECUTION OF DIFFERENT WORKS RELATED TO BHALKA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000577/2024-2025 | 2261/CD | 23/12/2024 | 21/02/2025 | NABIN DEBNATH | 26.48 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | WALL PAINTING DESIGNING MAKING & ERECTING OF DB USING LOGO TAGLINE FOR COOCHBEHAR DISTRICT UNDER JJAM SUPPORT ACTIVITIES. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000621/2024-2025 | 2322/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 86.56 | 0 | 0 | 100
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000083/2025-2026 | 725/CD | 17/05/2025 | 15/08/2025 | MS HOSSEN ELECTRICALS | 31.08 | 0 | 0 | 100
11 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BHALKA PIPED WATER SUPPLY SCHEME | SM/15237 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000291/2025-2026 | 800/CD | 23/05/2025 | 21/08/2025 | MATARA CONSTRUCTION CO. | 34.83 | 0 | 0 | 0
Total | [13 empty] | 20408.37 | 379.45 | 1.86