## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Duai Suai water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/001014/2023-2024 | 2596/NMD-II | 24/08/2023 | 23/09/2023 | THE BANERJEE CONCERN | 21.85 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 31/CD | 05/01/2024 |  | Resource Division | 18.7 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DUAISUAI TW II. |  |  | BILL/00334/2024-2025 | BP-107/24-25 | 21/05/2024 |  | WBSEDCL | 5.46 | 0 | 0 | null
4 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DUAISUAI TW II. |  |  | BILL/00334/2024-2025 | BP-107/24-25 | 21/05/2024 |  | WBSEDCL | 5.46 | 0 | 0 | null
5 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DUAI SUAI TW I. |  |  | BILL/00335/2024-2025 | BP-108/24-25 | 21/05/2024 |  | WBSEDCL | 3.02 | 0 | 0 | null
6 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Execution of different works related to DUAI SUAI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000545/2023-2024 | 639/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 95.71 | 0 | 0 | 60
7 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part H | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000586/2023-2024 | 623/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 77.82 | 0 | 0 | 100
8 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Execution of different works related to DUAI SUAI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1342/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000565/2022-2023 | 1959/CD | 24/03/2023 | 21/08/2023 | MS SSB CONSTRUCTION CO | 600.94 | 332.92 | 55.4 | 85
Total | [13 empty] | 20618.23 | 332.92 | 1.61