## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Execution of different works related to DUAI SUAI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1342/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000565/2022-2023 | 1959/CD | 24/03/2023 | 21/08/2023 | MS SSB CONSTRUCTION CO | 600.94 | 523.11 | 87.05 | 85
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Duai Suai water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001014/2023-2024 | 2596/NMD-II | 24/08/2023 | 15/04/2025 | THE BANERJEE CONCERN | 21.85 | 0 | 0 | 100
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Execution of different works related to DUAI SUAI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000545/2023-2024 | 639/CD | 11/03/2024 | 10/05/2024 | MS SSB CONSTRUCTION CO | 95.71 | 52.79 | 55.16 | 60
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part H | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000586/2023-2024 | 623/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 77.82 | 26.03 | 33.45 | 100
6 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within DUAI SUAI & BHURUKULDANGA area) KHARIJA KHAWARDARA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000618/2024-2025 | 2319/CD | 23/12/2024 | 19/08/2025 | KAJAL KUMAR DE | 72.8 | 0 | 0 | 50
7 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 31/CD | 05/01/2024 | 05/01/2024 | Resource Division | 18.7 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DUAISUAI TW II. |  |  | BILL/00334/2024-2025 | BP-107/24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL | 5.46 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DUAI SUAI TW I. |  |  | BILL/00335/2024-2025 | BP-108/24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL | 3.02 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | EXECUTION OF DIFFERENT WORKS (within ANGARKATA PARADUBI & DUAI SUAI area) RELATED TO UNISHBASHA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000681/2024-2025 | 87/CD | 17/01/2025 | 18/03/2025 | M/S KAMAK ENGINEERS AND CO | 89.87 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000031/2025-2026 | 597/CD | 28/04/2025 | 23/01/2026 | SHRI ANNAPURNA DISTRIBUTORS | 67.29 | 0 | 0 | 30
12 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | DUAI SUAI PIPED WATER SUPPLY SCHEME. | SM/15911 | New | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 74/CD | 15/01/2025 | 15/01/2025 | Resource Division | 30.8 | 0 | 0 | 0
Total | [13 empty] | 20873.54 | 601.93 | 2.88