## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BRAHMOTTAR CHATRA TW NO. II |  |  | BILL/02615/2023-2024 | BP-2023-24-578 | 01/02/2024 | 01/02/2024 | WBSEDCL | 12.46 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BRAHMOTTAR CHATRA TW NO. I |  |  | BILL/02617/2023-2024 | BP-2023-24-579 | 01/02/2024 | 01/02/2024 | WBSEDCL | 7.47 | 0 | 0 | 0
3 | COOCHBEHAR | Sitai | Coochbehar Division | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | Execution of different works related to BRAHMOTTAR CHATRA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1286/1-5/NBC-1; Dt.: 17-03-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000620/2022-2023 | 1904/CD | 17/03/2023 | 09/02/2026 | AMBITIOUS ENTERPRISE | 433.2 | 282.77 | 65.27 | 25
4 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Brahmottar Chatra water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001009/2023-2024 | 2591/NMD-II | 24/08/2023 | 02/09/2025 | M/S P.P ELECTRICALS | 21.3 | 0 | 0 | 50
5 | COOCHBEHAR | Sitai | Coochbehar Division | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR | Sitai | Coochbehar Division | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | EXECUTION OF DIFFERENT WORKS RELATED TO KONACHATRA ZONE-I & BRAHMOTTAR CHATRA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000529/2024-2025 | 2213/CD | 23/12/2024 | 19/10/2025 | AMBITIOUS ENTERPRISE | 64.6 | 0 | 0 | 60
7 | COOCHBEHAR | Sitai | Coochbehar Division | BRAHMOTTAR CHATRA PIPED WATER SUPPLY SCHEME. | SM/15912 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN ANANDARAN SINGIMARI AREA ) BRAHMOTTAR CHATRA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000578/2024-2025 | 2262/CD | 23/12/2024 | 21/02/2025 | GOUTAM KUMAR DAS | 33.98 | 0 | 0 | 100
Total | [13 empty] | 20362.3 | 282.77 | 1.39