## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Providing FHTC & other allied works at TUTIARKUTHI ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000362/2022-2023 | 1015/CD | 29/09/2022 | 29/10/2022 | SHYAMAL NATH | 9.98 | 9.93 | 99.53 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Execution of different works related to Aug. of TUTIARKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000087/2023-2024 | 622/CD | 12/07/2023 | 09/12/2023 | MS SSB CONSTRUCTION CO | 288.61 | 203.11 | 70.38 | 38
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Tutiarkuthi Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001204/2023-2024 | 2950/NMD-II | 10/11/2023 | 01/09/2025 | TAPAN BISWAS | 10.89 | 0 | 0 | 80
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Execution of different works related to TUTIARKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000394/2023-2024 | 1366/CD | 05/12/2023 | 03/02/2024 | MS SSB CONSTRUCTION CO | 68.3 | 53.38 | 78.16 | 78
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Execution of different works related to TUTIARKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000060/2024-2025 | 1309/CD | 16/07/2024 | 14/10/2024 | MS SSB CONSTRUCTION CO | 90.43 | 84.01 | 92.9 | 30
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | FUEL BILL |  |  | BILL/02031/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 2.07 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | SUPPLY DISEL TFG (BALABHUT, CHHITTILAI) |  |  | BILL/00589/2024-2025 | BP-223 | 01/08/2024 | 01/08/2024 | GOUTAM KUMAR DAS | 0.71 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Charges for new service connection at Tutiar kuthi PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/01035/2024-2025 | BP-305/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 7.02 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | FUEL BILL |  |  | BILL/00588/2024-2025 | BP-222 | 01/08/2024 | 01/08/2024 | SUCHITRO FUEL STATION | 0.6 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | FUEL BILL |  |  | BILL/02079/2023-2024 | BP-1420 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 2.07 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000069/2025-2026 | 645/CD | 05/05/2025 | 01/11/2025 | BIJOY ROY | 69.05 | 0 | 0 | 70
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000329/2025-2026 | 704/CD | 17/05/2025 | 12/01/2026 | MS SSB CONSTRUCTION CO | 85.29 | 0 | 0 | 100
Total | [13 empty] | 20424.3 | 350.44 | 1.72