## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Providing FHTC & other allied works at TUTIARKUTHI ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000362/2022-2023 | 1015/CD | 29/09/2022 | 29/10/2022 | SHYAMAL NATH | 9.98 | 9.93 | 99.53 | 1
2 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Tutiarkuthi Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,,Apd. |  |  | ORD/001204/2023-2024 | 2950/NMD-II | 10/11/2023 | 10/12/2023 | TAPAN BISWAS | 10.89 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Execution of different works related to TUTIARKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000394/2023-2024 | 1366/CD | 05/12/2023 | 03/02/2024 | MS SSB CONSTRUCTION CO | 68.3 | 29.68 | 43.45 | 78
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | FUEL BILL |  |  | BILL/02031/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 2.07 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | FUEL BILL |  |  | BILL/02079/2023-2024 | BP-1420 | 31/03/2024 |  | R.C BANIK BANIK & SONS | 2.07 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Execution of different works related to Aug. of TUTIARKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000087/2023-2024 | 622/CD | 12/07/2023 | 09/12/2023 | MS SSB CONSTRUCTION CO | 288.61 | 123.47 | 42.78 | 38
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Execution of different works related to TUTIARKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000060/2024-2025 | 1309/CD | 16/07/2024 | 14/10/2024 | MS SSB CONSTRUCTION CO | 90.43 | 0 | 0 | 30
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Charges for new service connection at Tutiar kuthi PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/01035/2024-2025 | BP-305/24-25 | 22/08/2024 |  | WBSEDCL | 7.02 | 0 | 0 | null
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | SM/15930 | Augmentation | Charges for new service connection at Tutiar kuthi PWSS, P/H-III in the dist of Coochbehar. |  |  | BILL/01035/2024-2025 | BP-305/24-25 | 22/08/2024 |  | WBSEDCL | 7.02 | 0 | 0 | null
Total | [13 empty] | 20275.66 | 163.08 | 0.8