## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA GADAIKHORAPIPED WATER SUPPLY SCHEME | SM/15931 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 1379/CD | 22/12/2022 |  | Resource Division | 68.08 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA GADAIKHORAPIPED WATER SUPPLY SCHEME | SM/15931 | Augmentation | Providing FHTC, laying of Pipe line and other allied works at BARO GADAIKHORA PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000072/2022-2023 | 269/CD | 24/05/2022 | 23/07/2022 | BIJOY ROY | 39.76 | 35.68 | 89.76 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA GADAIKHORAPIPED WATER SUPPLY SCHEME | SM/15931 | Augmentation | Execution of different works related to Aug. of BARA GADAIKHORA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000043/2023-2024 | 467/CD | 02/06/2023 | 30/10/2023 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 189.15 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA GADAIKHORAPIPED WATER SUPPLY SCHEME | SM/15931 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Baragodaikhora Water Supply Scheme TW No.I under NMD-II,PHE.Dte,Apd. |  |  | ORD/000922/2023-2024 | 2505/NMD-II | 14/08/2023 | 13/09/2023 | BLUE PINE | 10.53 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA GADAIKHORAPIPED WATER SUPPLY SCHEME | SM/15931 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery including other related accessories of Baragodaikhora( Replacement Tubewell) Water Supply Scheme at H/W Site under NMD-II,PHE.Dte Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000878/2022-2023 | 690/NMD-II | 28/03/2023 | 27/04/2023 | MADHAB SAHA | 1.81 | 1.02 | 56.68 | 100
Total | [13 empty] | 309.33 | 36.71 | 11.87